SEN381 - SOFTWARE ENGINEERING 381

CivicConnect

Project Engineering Document (PED) v4.0 Final

| Team Name | Git Gud |
| --- | --- |
| Team Members | Rivan Maritz Nicholas Armin Vronka Michiel Coenraad TerBlanche |
| Module | SEN381 - Software Engineering 381 |
| Document Version | V4.0 Final |
| Date | 18/10/2026 |
| Lecturer | Tendai Mkwaira |

# Document Control.

| Version | Date | Author(s) | Summary of Change | Approved By |
| --- | --- | --- | --- | --- |
| V 0.2 | 08/09 | Michiel Coenraad TerBlanche | Added the Problem Statement, Business Needs, Stakeholder Analysis, Scope and Requirements | Rivan Maritz |
| V 0.3 | 08/09 | Nicholas Armin Vronka | Added the Initial Risk Register and Initial Engineering Decision Log. | Michiel Coenraad TerBlanche |
| V 1.0 | 09/09 | Rivan Maritz | Added Assumptions & Constraints, Initial RTM, Process & Working Agreement, Deployment Considerations | Nicholas Armin Vronka |
| V 1.1 | 20/09 | Rivan Maritz | Added Data Persistence, Decision stack and design decision as well added new requirements and engineer log entries | Michiel Coenraad TerBlanche |
| V 1.2 | 23/09 | Nicholas Armin Vronka | Updated the RTM, MS2 Initial Design Decision, End-To-End Traceability Demonstration, Application/ Technical Documentation for README, Architecture, Technology & Initial Design Baseline. | Rivan Maritz |
| V 2.0 | 25/09 | Michiel Coenraad TerBlanche | Reviewed and evolved M1 requirements into a controlled change register (CR-01 to CR-06); added ASRs & quality drivers, the architecture decision and diagrams (ADR-M2-02), and the deployment-compatibility section (ADR-M2-03, ADR-M2-01-A1). | Nicholas Armin Vronka |
| V 3.0 | 16/10 | Nicholas Armin Vronka | Started PED v3.0 for M3: added Sections 25 to 41 (submission block, M2 conformance, controlled changes CC-01 to CC-06, CI design, quality strategy, test mapping and plan, performance plan, staging, defect and technical debt registers, risk update, RTM Part C, release summary, AI register additions, action list). Updated cover version. Sections 1 to 24 unchanged. | Rivan Maritz |
| V 4.0 | 18/10 | Rivan Maritz | Finalised PED v3.0 as PED v4.0 for Milestone 4 (closure). Sections 1 to 41 preserved; status fields in Sections 25, 29, 30, 35, 36, 38 and 39 updated in place. Added Sections 42 to 53: final submission block, release baseline, M1 scope to final delivery reflection, Scope Completion Percentage, final acceptance evidence, M3 issue closure, decisions and ADR-M3-01 draft, final RTM Part D, deployment and go-live decision, project reflection, limitations and future work, submission checklist and outstanding actions. | Michiel Coenraad TerBlanche |

Contents

Document Control.	2

1. Problem Statement, Business Need & Stakeholder Analysis	7

1.1	Problem Statement	7

1.2 Business Need	7

1.3 Stakeholder Analysis	7

2. Scope Baseline	8

2.1 In Scope	8

2.2 Out of Scope	8

2.3 Future / Optional Scope	8

3. Requirements	9

3.1 Functional Requirements	9

3.2 Non-Functional Requirements	11

4. Assumptions & Constraints	13

4.1 Assumptions	13

4.2 Constraints	14

5. Requirements Traceability Matrix (RTM) - Initial	14

6 Data & Persistence Baseline	16

7. Technology-Stack Decision - ADR-M2-01	18

8. Design Decision - Controlled Status Transitions (FR-010)	19

9. Process / Project Approach & Team Working Agreement	20

9.1 Process / Project Approach	20

9.2 Team Working Agreement	20

10. Initial Risk Register	20

11. Initial Engineering Decision Log	24

12. Updated Requirements Traceability Matrix	26

13. Initial Design Decision	29

14. End-to-End Traceability Demonstration	30

15. Application/ Technical Documentation for README	30

CivicConnect — Community Service Request Management Platform (SEN381, Team "Git Gud")	30

16. Architecture, Technology and Initial Design Baseline	31

16.1 What Is Included in Baseline v2.0	31

16.2 Known Open/ Deferred Decisions (not yet part of the baseline)	31

17. GitHub Repository & Governance	32

17.1 Repository Details	32

17.2 Governance Controls Checklist	32

18. AI Usage Register	33

19. Initial Deployment / Operational Considerations	35

20. M1 Baseline Review & Requirements Evolution	36

20.1 Review scope and outcome	36

20.2 Change request register	36

20.3 Data-model delta (input to Section 6)	37

20.4 Assumptions and constraints review	38

20.5 Effect on the baseline and the RTM	38

21. Architecturally Significant Requirements & Quality Drivers	39

21.1 ASR register	39

21.2 Priority order	40

21.3 Considered and not treated as architecture drivers	41

21.4 Tensions and how they are resolved	41

21.5 RTM link (input to the "ASR / Quality Driver" column)	41

22. Architecture Decision & Diagrams (ADR-M2-02)	42

22.1 Alternatives considered	42

22.2 Selected architecture: modules and diagrams	43

22.3 ADR-M2-02: Modular monolith	45

22.4 Architecture, technology and deployment kept apart	46

23. Deployment Compatibility (M2)	47

23.1 Deployment direction (ADR-M2-03 / ED-010)	47

Candidates and what the evidence says:	47

23.2 Are the M2 decisions plausible for this direction?	48

23.3 Configuration, secrets and networking	49

23.4 Versions and platform support (proposed amendment ADR-M2-01-A1)	49

23.5 Risks raised (proposed additions to the Risk Register)	50

23.6 Deliberately deferred decisions and the evidence still needed	51

24. Baseline Sign-Off	52

Sign-Off	52

25. M3 Submission Information (PED v3.0)	53

26. M3 Overview and Current Build Status	53

26.1 Repository state at the start of M3 (16/10/2026)	53

26.2 Agreed M3 core scope	53

26.3 Path to the release candidate	54

27. M2 Baseline Conformance	54

28. Controlled Changes	54

28.1 Engineering Decision Log additions	55

29. Construction and Configuration Control	55

30. CI and Automated Verification	56

30.1 What a green pipeline does and does not show	56

31. Quality Strategy Applied	56

32. Black-Box, Integration and System Validation	57

32.1 Existing automated tests (Java-Backend branch)	57

32.2 Gaps against the M3 minimum	58

32.3 Planned API / integration tests (PostgreSQL in CI)	58

32.4 Planned E2E / system tests (against staging)	58

33. Performance and Load Test (P-01)	59

34. Staging / Test Environment	59

35. Defects and Findings Register	60

36. Technical Debt Register	61

37. Risk Register Update (M3 review)	62

38. RTM v3.0 Part C: Implementation and Verification	63

39. Release Evidence Summary and Residual Risk	64

40. AI Usage Register: M3 Additions	64

41. Outstanding M3 Actions	65

42. M4 Submission Information (PED v4.0 Final)	66

43. Final Release Baseline and What Changed Since M3	66

43.1 Changes between the M3 release candidate plan and the final build	66

43.2 What M4 deliberately did not add	67

44. M1 Scope to Final Delivery	67

44.1 In-scope commitments (Section 2.1)	67

44.2 Non-functional commitments (Section 3.2)	68

44.3 Out of scope and future items (Sections 2.2 and 2.3)	68

44.4 Approved scope changes	69

45. Scope Completion Percentage	69

45.1 How far the result can be trusted	69

46. Final Acceptance and Verification Evidence	70

46.1 Execution status of the verification evidence	70

46.2 Critical journeys and acceptance criteria re-checked	70

47. M3 Issue Closure	71

47.1 Summary	71

47.2 Risk register: final status	71

48. Decisions and Controlled Changes: Final Status	72

48.1 Controlled changes	72

48.2 ADR-M3-01: Authentication mechanism (draft for approval)	72

48.3 Decisions with the clearest consequences	72

49. Final RTM Part D: Final Implementation, Evidence and Status	73

50. Final Deployment and Go-Live Decision	74

50.1 Staging evidence available	74

50.2 Why production is a no-go	74

50.3 Final release classification	75

50.4 Rollback	75

51. Final Project Reflection and Conclusion	75

52. Known Limitations and Future Work	76

53. Final Submission Checklist and Outstanding Actions	76

53.1 Brief checklist (Final Project brief, Section 16)	76

53.2 Outstanding actions before submission	76

References	77

# 1. Problem Statement, Business Need & Stakeholder Analysis

## Problem Statement

CivicConnect currently manages service requests, facility faults, damaged equipment, security concerns, IT support, maintenance issues, lost property and other operational requests through a fragmented mix of email, telephone calls, WhatsApp messages, spreadsheets and paper records. This produces several recurring problems:

- Requests are duplicated, overlooked, incorrectly assigned or lost between channels.

- Requesters have little to no visibility of whether a request was received, assigned, delayed, resolved or closed.

- Staff struggle to prioritise requests, identify ownership and coordinate work across channels.

- There is weak accountability for who changed a request's status and what action was actually taken.

- Management lacks reliable information on outstanding, overdue and resolved work.

- Reporting is manual, inconsistent and difficult to audit.

- Sensitive request information is handled inconsistently across informal channels.

- No single controlled record exists for the lifecycle of a request.

## 1.2 Business Need

CivicConnect needs a controlled digital platform where they can gain access to a reliable, traceable and usable way to submit, manage and report on service requests. This is to improve the visibility and accountability without creating an unsustainable technical, operational or financial burden

## 1.3 Stakeholder Analysis

| Stakeholder | Role / Interest | Needs / Expectations | Influence (H/M/L) | Notes |
| --- | --- | --- | --- | --- |
| Requester (Community member) | Submits and tracks service requests | Fast and simple submissions visibility of status and the confidence of the report being received | L | They want a full detail on who is handling the request and when it will be done, but this may conflict with the organisation that may restrict staff-identity/scheduling detail for operational and privacy reasons |
| Frontline staff | Receives, actions and updates requests | Clear queue of relevant requests and the ability to filter/sort as well as a simple status-update mechanism | M | They want minimal mandatory data entry, but management wants structured, complete data for reporting |
| Supervisor / coordinator | Assigns and oversees request handling | Full request detail, the ability to reassign and visibility of overdue items | H | Wants flexible reprioritisation, but requesters expect fair, first-in-first-out handling |
| Management / oversight | Accountable for service performance | Reliable open/overdue/resolved reporting by category and status | H | Wants fine-grained reporting detail, but this conflicts with data-minimisation and requester-privacy expectations |
| Organisation / project sponsor | Commissions and accepts the system | Delivery within the team's schedule and near-zero cost, demonstrable value | H | May request scope additions not in the current baseline |
| Development team | Designs, builds, secures and defends the platform | Clear, stable, testable requirements, controlled scope | H | Wants scope discipline, but sponsor/stakeholders may push for 'nice to have' additions |

# 2. Scope Baseline

## 2.1 In Scope

- Requester: submit a new service request with category, description and relevant details.

- Requester: categorise a request using a controlled (predefined) category list.

- Requester: view the current status of a submitted request.

- Requester: view a history/list of previously submitted requests.

- Requester: receive meaningful feedback when a request is accepted, rejected, updated or completed.

- Staff: view requests relevant to their authorisation.

- Staff: search, filter and sort requests by useful criteria (category, status, age).

- Staff: view full request detail.

- Staff: assign or accept responsibility for a request.

- Staff: update request status through controlled transitions.

- Staff: record actions, comments or resolution information against a request.

- Staff: resolve or close requests where authorised.

- Management: view service activity information (open, overdue, resolved, closed).

- Management: view requests by category/status or another justified dimension.

## 2.2 Out of Scope

- Payment processing or billing for any service.

- Automated, rules-based or AI-driven request-routing/assignment (manual assignment only for the baseline).

- Integration with external emergency-service or third-party dispatch systems.

- Native mobile applications (a responsive web interface satisfies the baseline).

## 2.3 Future / Optional Scope

- Automated or optimised assignment of requests to staff/teams.

- Requester satisfaction survey after resolution.

- Public-facing analytics/reporting dashboard

# 3. Requirements

## 3.1 Functional Requirements

| ID | Requirement | Source | Priority | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| FR-001 | The system will allow a requester to submit a new service request with category, description and the relevant supporting details. | Requester | High | Given a requester on the submission form, when they select a category, enter a description (>= 10 characters) and submit, then the request is saved and a unique reference is displayed within 3 seconds. |
| FR-002 | The system will require a requester to categorise a request using a predefined, controlled category list. | Requester | High | In the submission form, when no category is selected, the submission will be blocked, and a validation message will be shown. When a category is selected, then it is stored against the request unchanged from the controlled list. |
| FR-003 | The system will allow a requester to view the status of a submitted request. | Requester | High | Given a requester view one of their own requests, when the page loads, then the current lifecycle stage and the date it was last updated are displayed. |
| FR-004 | The system will allow a requester to view a history/list of their previously submitted requests. | Requester | High | Given a requester with 2 or more prior requests, when they open their request history, then every request they submitted is listed with its reference, category and status. |
| FR-005 | The system will notify the requester with meaningful feedback when a request is accepted, rejected, updated or completed. | Requester | High | Given a staff member changes a request's status, when the change is saved, then the requester's view of that request reflects the new status and a status-specific message within 1 minute. |
| FR-006 | The system will display to staff only the requests they are authorised to view. | Staff | High | Given a staff account with a defined authorisation scope, when they open the request queue, then only requests within their authorised category/team are listed. |
| FR-007 | The system will allow staff to search, filter and sort requests by category, status and request age. | Staff | High | Given the staff queue, when a staff member applies a category filter and sorts by age descending, then only matching requests are shown, oldest first. |
| FR-008 | The system will allow staff to view full detail of a request. | Staff | High | Given a request in the queue, when a staff member opens it, then category, description, requester reference, status history and any recorded actions/comments are displayed. |
| FR-009 | The system will allow staff to assign or accept responsibility for a request. | Staff | High | Given an unassigned request, when an authorised staff member assigns it, then the request's owner and assignment timestamp are recorded. |
| FR-010 | The system will allow staff to update a request's status only through a controlled set of valid transitions. | Staff | High | Given a request in status "Submitted", when staff attempt to set it directly to "Resolved", then the transition is rejected unless it passes through the defined intermediate stages, valid transitions succeed and are timestamped. |
| FR-011 | The system will allow staff to record actions, comments or resolution information against a request. | Staff | High | Given an assigned request, when staff adds a comment or resolution note it gets stored with the author timestamp will be visible in the request’s history |
| FR-012 | The system shall allow authorised staff to resolve or close a request. | Staff | High | Given a request with recorded resolution, when a staff member who is authorized marks the request resolved, its status will change to “Resolved”. A resolution timestamp will be made, stored and the request becomes a read only |
| FR-013 | The system will allow management to view service activity information across all requests. | Management | High | Given a manager account, when they open the activity view they can they will get aggregate counts of requests by status displayed by a selectable date range (default 7 days) |
| FR-014 | The system shall allow management to identify open, overdue, resolved and closed requests. | Management | High | Given an assigned overdue threshold per category, when management opens the activity view requests succeeding the assigned threshold are marked as overdue |
| FR-015 | The system will allow management to view requests by category, status or another justified dimension. | Management | Medium | Given the activity view, when management selects a category filter, then counts and listings update to reflect only that category. |
| FR-016 | The system will provide management with sufficient information to support accountability and service-performance analysis. | Management | Medium | Given a completed reporting period, when management exports or views a summary, then average time-to-resolution per category is shown, traceable to the underlying request records. |

## 3.2 Non-Functional Requirements

| ID | Quality Attribute | Requirement | Measure / Target | Priority |
| --- | --- | --- | --- | --- |
| NFR-001 | Request submission will respond within an acceptable time under normal load. | A load test at 50 concurrent virtual users shows a 95th-percentile submission-confirmation time <= 3 seconds. | 95% of submissions confirmed within 3 seconds at up to 50 concurrent users | Medium |
| NFR-002 | Every request will be given a unique tracking reference. | An automated test generating 100,000 references reports zero collisions. | Zero duplicate references across 100,000 generated records | High |
| NFR-003 | Requester personal and request data shall be protected from unauthorised access. | Access restricted by authenticated role. No personal data exposed via public/unauthenticated endpoints | An independent review/scan confirms personal-data fields are access-controlled and are not present in any public-facing endpoint or log output. | High |
| NFR-004 | The system will be available during normal operating hours. | >= 99% uptime during defined business hours, measured monthly | An uptime-monitoring report over a 30-day period shows >= 99% availability within the defined window. | Medium |
| NFR-005 | The submission process must be usable by requesters with limited digital literacy. | >= 80% of moderated test participants should complete submission unaided within 5 minutes | Usability-test session logs show ≥ 80% of participants completing submission without facilitator intervention within 5 minutes. | Medium |
| NFR-006 | Every status change shall be auditable. | 100% of status transitions logged with timestamp and actor | A query of the audit log for any request shows a complete, ordered history of status transitions with no gaps. | High |
| NFR-007 | The platform's operating cost should remain within the team's near-zero-cost constraint during the project. | Remains within free-tier limits of chosen hosting/services for the academic period | Platform billing/usage dashboard shows the project remains within the documented free-tier limits for the duration of the project. | High |

# 4. Assumptions & Constraints

## 4.1 Assumptions

| ID | Assumption | Area (Scope/Schedule/Cost/Resources/Quality/Security) | Risk if Invalid |
| --- | --- | --- | --- |
| AS-01 | Requesters have access to a smartphone, tablet or computer with a modern web browser and basic internet connectivity. | Scope | Some community members may be excluded from submitting digitally; an alternative low-tech intake channel would need to be added to scope. |
| AS-02 | Staff will check the platform for new or updated requests at least once per working day. | Quality | Requester-facing status/feedback expectations (e.g. FR-005) become unachievable regardless of system performance. |
| AS-03 | The organisation does not currently operate an existing digital system whose historical request data must be migrated into CivicConnect. | Scope | A data-migration requirement would need to be added, expanding the Milestone 1 scope baseline. |
| AS-04 | The team's chosen technology stack and hosting platform will be compatible with, or installable on, the BC Desktop / available development environment. | Resources | Development could stall until an alternative environment or platform is sourced, risking the milestone schedule. |
| AS-05 | A free or low-cost hosting tier will provide sufficient capacity for demonstration and testing throughout the academic year. | Cost | The team may need to fund hosting out of pocket, or the NFR-007 cost target would need to be revisited. |
| AS-06 | All three team members will have continued access to GitHub and development tools for the full project duration. | Resources | Individual contribution evidence could be interrupted, affecting both team and individual milestone assessment. |

## 4.2 Constraints

| ID | Constraint | Area | Impact on Project |
| --- | --- | --- | --- |
| CO-01 | Team size is fixed at exactly 3 students. | Resources | All scope and schedule decisions must be sized for 3 people; no additional development capacity is available. |
| CO-02 | The project must progress through 4 formal milestones within the SEN381 delivery period. | Schedule | Requirements and scope must be baselined early enough that unresolved M1 decisions do not block later milestones. |
| CO-03 | The team should prefer free or low-cost services where practical. | Cost | Technology and hosting choices are constrained to free-tier or near-zero-cost options for the academic year (see NFR-007). |
| CO-04 | Approved scope must be baselined and controlled; uncontrolled scope creep is not acceptable. | Scope | Any addition beyond Section 2.1/2.3 requires a formal change request (Master Brief, Section 14). |
| CO-05 | Security must be treated as a lifecycle-wide responsibility, not a final add-on. | Security | Security requirements (e.g. NFR-003) must be considered from Milestone 1 onward, not deferred to Milestone 3. |
| CO-06 | No technology stack, architecture or platform is prescribed by the module. | Technology | The team is fully responsible for researching and justifying its own technology decision with evidence at Milestone 2. |
| CO-07 | All three members must present and be individually examined at every milestone. | Schedule / Resources | Presentation slots and preparation time must be planned for every team member, regardless of how tasks were split. |

# 5. Requirements Traceability Matrix (RTM) - Initial

| Req ID | Description | Stakeholder / Source | Priority | Status |
| --- | --- | --- | --- | --- |
| FR-001 | Requester submits a new service request with category, description and details. | Requester | High | Draft |
| FR-002 | Requester categorises a request using a predefined, controlled category list. | Requester | High | Draft |
| FR-003 | Requester views the status of a submitted request. | Requester | High | Draft |
| FR-004 | Requester views a history/list of previously submitted requests. | Requester | High | Draft |
| FR-005 | Requester receives meaningful feedback when a request is accepted, rejected, updated or completed. | Requester | High | Draft |
| FR-006 | System displays to staff only the requests they are authorised to view. | Staff | High | Draft |
| FR-007 | Staff search, filter and sort requests by category, status and age. | Staff | High | Draft |
| FR-008 | Staff view full detail of a request. | Staff | High | Draft |
| FR-009 | Staff assign or accept responsibility for a request. | Staff | High | Draft |
| FR-010 | Staff update a request's status only through controlled valid transitions. | Staff | High | Draft |
| FR-011 | Staff record actions, comments or resolution information against a request. | Staff | High | Draft |
| FR-012 | Authorised staff resolve or close a request. | Staff | High | Draft |
| FR-013 | Management views service activity information across all requests. | Management | High | Draft |
| FR-014 | Management identifies open, overdue, resolved and closed requests. | Management | High | Draft |
| FR-015 | Management views requests by category, status or another justified dimension. | Management | Medium | Draft |
| FR-016 | Management has sufficient information to support accountability and service-performance analysis. | Management | Medium | Draft |
| NFR-001 | Request submission responds within an acceptable time under normal load. | Requester | Medium | Draft |
| NFR-002 | Every request is given a unique tracking reference (zero collisions). | Requester | High | Draft |
| NFR-003 | Requester personal and request data is protected from unauthorised access. | Management / Dev team | High | Draft |
| NFR-004 | System is available during normal operating hours (>=99% uptime). | Staff | Medium | Draft |
| NFR-005 | Submission process is usable by requesters with limited digital literacy. | Requester | Medium | Draft |
| NFR-006 | Every status change is auditable (actor + timestamp logged). | Management | High | Draft |
| NFR-007 | Platform operating cost remains within the team's near-zero-cost constraint. | Organisation / sponsor | High | Draft |

# 6 Data & Persistence Baseline

Key Entities & Relationships

- User - id, name, email, passwordHash, role (REQUESTER / STAFF / MANAGER)

- ServiceRequest - id, referenceNumber (unique), categoryId, description, status, priority, requesterId, assignedStaffId, createdAt, updatedAt

- Category - id, name, active (controlled list per DEC-01 / FR-002)

- StatusHistory - id, requestId, previousStatus, newStatus, changedBy, changedAt, comment (drives NFR-006 auditability)

Relationships: User 1 to many ServiceRequest (as requester) and 1 to many ServiceRequest (as assigned staff); ServiceRequest many to 1 Category; ServiceRequest 1 to many StatusHistory.

Persistence Model & Justification

Decision: Relational database (PostgreSQL) via Spring Data JPA

Justification against structure, relationships, access patterns, integrity, consistency and growth:

- ServiceRequest data is inherently relational (users, categories, status history) with clear foreign-key relationships - a natural fit for a relational schema rather than a document store.

- Status transitions and their audit trail (NFR-006) require atomic, consistent writes across two tables (ServiceRequest + StatusHistory) - PostgreSQL's ACID transactions handle this directly.

- Unique tracking references (NFR-002) are enforced with a database-level UNIQUE constraint, backed by an application-level check - stronger correctness guarantee than an eventually consistent store.

- Spring Data JPA reduces repository boilerplate, which matters for the team's 3-person / 4-milestone schedule (CO-01, CO-02).

- Mature free-tier managed PostgreSQL options (e.g. Render, Neon, Supabase) satisfy the near-zero-cost constraint (CO-03, NFR-007).

Alternative considered: MongoDB (document store)

Rejected - ServiceRequest data is highly relational and needs strong consistency for status transitions and the audit trail; enforcing that in a document model would require more application-level integrity logic than a relational schema provides natively. The team also has more relevant coursework exposure to relational database design, reducing learning-curve risk (AS-04).

Integrity, Consistency & Architecture-Level Reliability

- Status transitions are validated in the domain layer (see Section 5.6 design decision) before being persisted, inside a single @Transactional boundary covering both the ServiceRequest update and its StatusHistory row - no orphaned audit entries if either write fails.

- Foreign-key constraints from ServiceRequest to User and Category prevent orphaned records.

- Indexes on requesterId, assignedStaffId, category and status support the filtering/sorting required by FR-007 without a later redesign.

- Single-instance managed PostgreSQL is an accepted single point of failure at this stage, proportionate to CivicConnect's expected community-scale volume and the team's cost constraint (CO-03) - logged as a known limitation, not solved now.

Backup relies on the chosen managed hosting provider's automated backups where the free tier includes them; to confirm and document once a specific provider is selected.

# 7. Technology-Stack Decision - ADR-M2-01

Context: CivicConnect requires a backend capable of enforcing role-based access (FR-006), controlled status transitions (FR-010) and auditable data changes (NFR-006), deployable within a near-zero-cost constraint (NFR-007, CO-03) by a 3-person team on a fixed milestone schedule (CO-01, CO-02).

Alternatives Considered

| Option | Stack |
| --- | --- |
| A | Java + Spring Boot + Spring Data JPA + Spring Security + PostgreSQL |
| B | Node.js + Express + Prisma/TypeORM + PostgreSQL |
| C | Python + Django + Django ORM + PostgreSQL |
| D | .NET + ASP.NET Core + Entity Framework Core + PostgreSQL / SQL Server |

Decision: Option A - Java + Spring Boot + Spring Data JPA + Spring Security for the backend REST API, with PostgreSQL for persistence. Frontend framework to be confirmed with the team's Web App Lead; consumes the backend via REST.

Rationale & Trade-offs

- Team capability: existing Java coursework exposure lowers the learning curve for backend structure versus adopting an unfamiliar language - directly reduces the risk logged in AS-04/CO-01.

- Security ecosystem: Spring Security provides mature, well-documented role-based access control, directly supporting FR-006 and NFR-003 with less custom code than a lighter framework would require.

- Maintainability: Spring's layered controller/service/repository structure separates concerns cleanly, which also supports the design-pattern work.

- Testing/tooling: JUnit 5, Mockito and Spring Boot Test are mature and well documented.

- Deployment compatibility: Spring Boot packages as a single executable JAR, deployable to free-tier platforms (e.g. Render, Railway, Fly.io) without complex multi-service orchestration - keeps within NFR-007/CO-03.

- Cost: all selected components are free/open-source; specific free-tier limits (connections, storage, sleep behaviour) to be documented once a provider is chosen.

Trade-off accepted: Spring Boot has a heavier initial setup/configuration overhead and larger memory footprint on free-tier hosting than a minimal framework (e.g. Express or Flask) - accepted because it's offset by the team's existing Java familiarity and Spring Security's built-in access-control tooling.

Versions & Compatibility

- Java 21 (LTS)

- Spring Boot 3.x

- PostgreSQL 15+

- Maven for build/dependency management

# 8. Design Decision - Controlled Status Transitions (FR-010)

Design problem: FR-010 requires that staff can only move a request through valid status transitions (e.g. Submitted → Assigned → In Progress → Resolved → Closed), never an invalid jump (e.g. Submitted → Closed directly). Left unmanaged, this validation risks being duplicated or inconsistently enforced across multiple controller/service methods as the codebase grows.

Alternatives Considered

- A. Factory Method Pattern

- B. State design pattern

- C. Strategy Pattern

Final Decision

Apply the State design pattern to ServiceRequest status handling: each status (Submitted, Assigned, In Progress, Resolved, Closed) is represented as its own state object responsible for knowing which transitions are valid from it, rather than validation logic scattered through if/switch conditionals in service methods.

Why It Fits CivicConnect

- Centralises transition rules in one place per status, directly supporting FR-010.

- Makes NFR-006 auditability straightforward - every transition attempt, valid or rejected, can be logged from a single point.

- A proportionate amount of structure for a small, well-defined set of statuses (justified against M2's proportional-architecture expectation - not adopted just because it was taught).

Benefit vs. Trade-off

Benefit: Reduced coupling (transition rules don't leak into controllers), improved testability (each state's allowed transitions can be unit-tested in isolation), easier to extend if a new status is added later.

Trade-off / complexity introduced: More classes than a simple enum-and-switch approach. For 5–6 well-defined states this is a deliberate, justified trade of some structural complexity for correctness and auditability - not premature over-engineering, but worth being able to defend that line if asked.

Affected Components

- ServiceRequestStatus (interface/abstract base)

- Concrete state classes: SubmittedState, AssignedState, InProgressState, ResolvedState, ClosedState

- ServiceRequest domain entity (holds current state)

- StatusTransitionService

# 9. Process / Project Approach & Team Working Agreement

## 9.1 Process / Project Approach

The team will work in short, milestone-aligned iterations. Each milestone's sub-deliverables are broken into issues on the GitHub project board and assigned to an owner (see Section 6.2). Work is reviewed by at least one other team member before being merged/finalised, and progress is checked at the team's weekly meeting. Each member is responsible for understanding not only their own section but the full PED, since all three members are individually examined at every milestone presentation.

## 9.2 Team Working Agreement

| Area | Agreement |
| --- | --- |
| Meeting cadence | Weekly check-in (day/time TBD by team) plus a short async status update in the team chat every 2-3 days. Ad-hoc calls before each milestone deadline. |
| Communication channel | Primary channel: [WhatsApp/Discord/Teams - team to confirm]. Expected response time within 24 hours on working days. |
| Roles this milestone | Member A: Problem/Scope/Requirements. Member B: Risk/Decisions/Governance. Member C: Traceability/Process/Baseline. Roles may rotate for later milestones by team agreement. |
| Git / branching conventions | Feature branches named feature/<short-description> or docs/<short-description>. Commit messages describe what changed and why, e.g. 'Add initial Risk Register entries for RR-01 to RR-04'. |
| Conflict resolution | Disagreements are discussed at the next check-in; if unresolved, decided by team majority vote and logged in the Engineering Decision Log; escalate to the lecturer only if it affects grading fairness. |
| Definition of done | A section/task is 'done' when it is committed to the repository, reviewed by at least one other team member, and cross-checked against the relevant Master Brief requirement. |

# 10. Initial Risk Register

| Risk ID | Description | Cause | Problem | Impact Priority | Priority | Mitigation | Project Contingency | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Outlined requirements created during planning get changed due to client feedback during milestone review. Invalidating sections of approved scope | Informal feedback that was received verbally in presentation of work rather than through formal Change Request Process | Medium | High | High | Require all proposed changes- no matter the origin to go through CR/ Impact analysis before it touches the project baseline. | Log proposed request as deferred until formal impact analysis approvals are completed. Ensure proper process is followed | Michiel Coenraad TerBlanche | Open |
| R-002 | Two-reviewer approval system gets bypassed due to a third member making decisions without team approval | Small team size, increasing pressure near deadlines, misplaced trust in own work | Medium | High | High | Configure branch protection to block self-approval of work while requiring 2 non-author reviews to qualify work. Rotate reviewers periodically. | Retroactively re-review work completed to ensure that it meets standards given. If not escalate to lecturer for remediation of work if control fails. | Nicholas Vronka | Open |
| R-003 | Sensitive service-request information (e.g. security concerns, complaint details) handled inconsistently before proper access controls are created. | No access-control requirements or data classification have been defined such as a Role Based Access Control system. | Medium | High | High | Define minimum handling Non-Functional Requirements (NFR) for who may view each field even when proper implementation is deferred to Milestone 2, restrict data categories until then. | Limit initial requests form to non-sensitive fields until proper access control is defined for the project. | Rivan Maritz | Open |
| R-004 | Schedule slippage in Milestone 2/3 as undefined project technology stack does not match team skill level. | Stack selection has been deferred to Milestone 2 leading to team skill profile not being assessed against candidate stack. | Medium | Medium | Medium | Capture team capability as an explicit weighted criterion in Milestone 2 technology decision matrix. Plan a short proof of concept in the meanwhile | Fall back to the most familiar stack that would satisfy the requirements even if limitations would need to recategorise to function. | Entire Team | Open |
| R-005 | Additional project features added without careful analysis of assigned consequence. | Team enthusiasm/ stakeholder demand outpaces set controlled change process. | Medium | Medium | Medium | Additional features must be tested against a Decision Log with trade-off analysis before they enter project baseline. | Reject suggestion or move it to a future scope deadline if it does not meet the current Milestone deadline. | Rivan Maritz | Open |
| R-006 | Repository evidence (commits/ issues) is produced in bursts near the deadline instead of progressively throughout the project. | Pressure from module coursework, assignments, milestone deadlines or real-life duty. | Medium | High | High | Weekly commit as outlined in Team Working Agreement that is facilitated at each team meeting. | Notify lecturer if a team member falls behind to set an intervention. | Nicholas Armin Vronka | Open |
| R-007 | AI-assisted work, code or functions are accepted into project baseline without adequate human verification conducted to ensure quality and correctness of work | Time pressure, comprehension failure of project requirements or lack of interest promote lax standards of AI output | Medium | Medium | Medium | Every AI contribution will need an AI Usage Register entry created and a recorded verification step to be fulfilled before implementation. | Flagged items are to be reworked and reverified before they can be added in the next baseline, any content unverified will be removed. | Rivan Maritz | Open |
| R-008 | Team's limited hands-on experience with Spring Security RBAC leads to a misconfigured or overly permissive authorization scheme. | Framework unfamiliarity, time pressure, no formal security review scheduled yet. | Med | High | High | Build and test authorization rules incrementally per role, starting with Requester before Staff/Management; pair-review all security config changes. | All members will learn the spring security system via YouTube videos and website tutoring sites. | Rivan Maritz | Open |
| R-009 | Free-tier limits (DB connections, cold-start, storage caps) on the chosen host are exceeded or cause demo downtime. | Team hasn't load-tested against the specific provider's free-tier limits yet. | Med | Med | Med | Document the provider's free-tier limits before committing (ADR-M2-01); test representative load before Milestone 3. | Use a small database for startup of business so that system can be tested before paid subscriptions are considered. | Rivan Maritz | Open |
| R-010 | Status-transition State pattern is only partially applied (e.g. a new status bypasses it), causing inconsistent enforcement. | Teammates unfamiliar with the pattern may mutate status directly under time pressure. | Low | Med | Med | Document the pattern's usage clearly in technical docs; review checks for direct status-field mutation outside the pattern. | All members will learn the state pattern design approach via YouTube videos and website tutoring sites. | Rivan Maritz | Open |

# 11. Initial Engineering Decision Log

| Decision ID | Context | Project Constraints | Alternatives Considered | Decision | Rationale / Trade-offs | Outlined Risks | Evidence | Later Consequences |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ED-001 | Milestone 1 explicitly excludes the finalised technology-stack selected but the team will need to plan for that later. | The schedule of fixed milestones, team capability not properly assessed, unknown security ecosystem added with requirements not matching project baseline. | A: Pick a familiar stack to get in “early progress” to show planning. B: Formally pre-agree on evaluation criteria. | Defer the tech-stack selection to Milestone 2, record criteria now (requirement fit, team capability, security, cost, deployment capability). | Choosing early could risk locking the project into unsuitable or unusable technology before requirements are outlined properly. Trade-off: no early code no risks at this stage. | R-004 | PE3D Forward Engineering Consideration section. | To be finalised with an ADR at Milestone 2 once stack is selected. |
| ED-002 | The brief states that there must be a protected-main and mandatory two-reviewer approval at the start of the project work, not just once the coding has begun. | 3-person project team means every project requirement demands full team engagement as there will always be 1 author and 2 reviewers. | A: Apply proper governance only once construction of project begins (Milestone 2/3). B: Apply this from the first Milestone 1 commit, covering documentation as well. | Enable branch protection and the 2-reviewer rule from day 1 of Milestone 1. Applied to code, registers and documentation | GitHub is an "an engineering control and evidence environment, not merely the place where final code is uploaded". Trade-off: Slow early document iteration for history. | R-002 | Repository branch protection settings. | Reviewed once Milestone 2 has begun. |
| ED-003 | Requester capabilities must be accessible from various devices, implementation of additional features if needed. | 3-student team, single-semester timeline, unconfirmed native mobile capability, cost of maintaining 2 codebases. | A: Native Mobile applications for project consideration. B: Only a responsive Web-app. C: Hybrid Framework to be implemented | Deliver a responsive web application only. Native mobile apps are currently out of scope. | A native web app satisfies all requirements from the 3 present stakeholders without increasing the workload. Consistent with the briefs point of a smaller, controlled, high-quality solution. | R-005 | PED Scope Baseline section. | Revisit only if a formal change request is justified for the project baseline. |
| ED-004 | Brief requires that unique, stable requirement IDs and one evolving Requirement Traceability Matrix (RTM) across all Milestones. | Multiple contributors that edit the work concurrently. Progress must stay stable and visible for traceability into Milestone 2. | A: Renumber requirement per their impact for each Milestone. B: Fix the ID scheme now and never need to renumber. | Adopt R-0XX/ED-0XX that is assigned sequentially, never reused, tracked in a single RTM file from Milestone 1 onwards. | Stable IDs are required for there to be a proper traceability chain. Trade-off: Numbering gaps will begin if a requirement is later removed, in exchange traceability integrity is stable. | R-001 | RTM file, PED requirements section. | Enforced at every future project baseline update. |
| ED-005 | Exclusion of detailed database design and detailed RBAC from Milestone 1, however R-003 shows why it is needed for access control to already exist. | Security requirement identified early in project development with detailed designs needing architecture-level analysis that has not yet been performed. | N/A | Defer the persistent technology and detailed RBAC model to Milestone 2 ADR, record only the NFR that support role-based access. | Commit to a data/access design before requirements are fully outlined with risks and constraints understood. No trade-off has been recorded yet as none exist until a decision is made. | R-003 | Forward Engineering Considerations register. | To become formal as the ADR in Milestone 2 of the project. |
| ED-006 | Backend/persistence technology selection for CivicConnect. | Team members need to work preferably with technology which is familiar. | A: Java+Spring Boot+PostgreSQL. B: Node+Express+PostgreSQL. C: Python+Django+PostgreSQL. D: .NET+ASP.NET Core+PostgreSQL | Java + Spring Boot + Spring Data JPA + Spring Security + PostgreSQL. | Existing Java coursework exposure and Spring Security's built-in RBAC reduce learning-curve risk (CO-01/AS-04) at the cost of heavier initial setup than a minimal framework. | R-008 | ADR-M2-01; A2 Task 2/4 research (cite actual source) | This will influence the design structure of the project. |
| ED-007 | Enforcing valid status transitions for service requests (FR-010). | staff can only move a request through valid status transitions (e.g. Submitted → Assigned → In Progress → Resolved → Closed), never an invalid jump (e.g. Submitted → Closed directly) | A: Factory Method Pattern B: State design pattern. C: Strategy Pattern. | Apply the State design pattern to ServiceRequest status. | Centralises transition rules and improves testability/auditability at the cost of more classes than a simple conditional approach - justified by the auditability requirement. | R-010 | Design record, Section 5.6; A2 Task 1 research (cite actual source) | This will enforce all users to follow the valid transitions at all times. |

# 12. Updated Requirements Traceability Matrix

RTM v2.0 — Part A: Requirement, Driver, Architecture, Data, Design & Technology

| ID | Requirement (short) | Pri. | ASR / Quality Driver | Architecture / Module | Data / Persistence Impact | Design / Interface Decision | Technology Decision | Implementation Evidence |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FR-001 | Submit new service request | High | Usability (NFR-005) | Request Submission Module (Controller/Service) | Creates ServiceRequest + links Category | N/A, standard form validation | Spring Boot REST + Spring Data JPA + PostgreSQL | Planned but not yet implemented |
| FR-002 | Controlled category selection | High | Data integrity | Request Submission Module | Category entity (controlled list, DEC-01) | N/A | Spring Data JPA + PostgreSQL | Planned |
| FR-003 | View request status | High | Auditability (NFR-006) | Request Status Module | ServiceRequest.status, StatusHistory | Reads current State object (ED-007) | Spring Boot REST + JPA | Planned |
| FR-004 | View request history/ list | High | Usability | Request Queue Module | ServiceRequest (read, filter by requesterId, indexed) | N/A | Spring Data JPA | Planned |
| FR-005 | Notify requester on change | High | Timeliness; NFR-006 | Notification Module (new) | ServiceRequest, StatusHistory | Observer Pattern (ED-008), NotificationService listens for StatusChangedEvent | Spring Boot event publisher/ listener + JPA | Design translated, coding not started yet |
| FR-006 | Role-based visibility for staff | High | Security (NFR-003) | Auth/ RBAC Module | User.role | N/A, Spring Security config | Spring Security (ADR-M2-01) | Planned |
| FR-007 | Search/ filter/ sort | High | Performance/ usability | Request Queue Module | Indexes: requesterId, assignedStaffId, category, status | N/A, repository query methods | Spring Data JPA query methods | Planned |
| FR-008 | View full request detail | High | Traceability | Request Queue Module | ServiceRequest + StatusHistory join | N/A | Spring Boot REST + JPA | Planned |
| FR-009 | Assign/ accept responsibility | High | Accountability | Assignment Module | ServiceRequest.assignedStaffId + StatusHistory entry | N/A (Strategy pattern considered for auto-assignment, Future Scope only) | Spring Boot REST + JPA | Planned |
| FR-010 | Controlled status transitions | High | NFR-006 (primary driver); Risk R-010 | Request Status Module | ServiceRequest.status, StatusHistory (atomic write, Sec.6) | State Pattern (ED-007) | Spring Boot Service layer + JPA @Transactional | Initial state classes drafted, to be committed |
| FR-011 | Record actions/comments | High | Auditability | Resolution Module | StatusHistory.comment | N/A | Spring Data JPA | Planned |
| FR-012 | Resolve/ close request | High | Data integrity (read-only after resolve) | Resolution Module | ServiceRequest.status = Resolved enforced read-only | State Pattern (ED-007), ResolvedState/ ClosedState | Spring Boot + JPA | Planned |
| FR-013 | Management activity view | High | Reporting | Reporting Module (new) | ServiceRequest aggregate/ count queries | N/A | Spring Data JPA projection queries | Planned |
| FR-014 | Identify open/ overdue/ resolved/ closed | High | SLA/ accountability | Reporting Module | ServiceRequest.createdAt vs category threshold | N/A (Strategy pattern per-category threshold, Future Scope) | Spring Data JPA | Planned |
| FR-015 | View by category/ status | Medium | Reporting | Reporting Module | ServiceRequest (group by category/ status) | N/A | Spring Data JPA | Planned |
| FR-016 | Accountability/ performance analysis | Medium | Reporting | Reporting Module | ServiceRequest + StatusHistory (avg. resolution time) | N/A | Spring Data JPA aggregate query | Planned |
| NFR-001 | Submission response time | Medium | Performance ASR | Request Submission Module | ServiceRequest insert path | N/A | Spring Boot stateless REST | Planned |
| NFR-002 | Unique reference, zero collisions | High | Data-integrity ASR | Request Submission Module | ServiceRequest.referenceNumber (DB UNIQUE constraint) | N/A | PostgreSQL UNIQUE + app-level check | Planned |
| NFR-003 | Protect personal/ request data | High | Security ASR (drives RBAC) | Auth/ RBAC Module | User.passwordHash; access-controlled ServiceRequest fields | N/A – Spring Security authorization | Spring Security (ADR-M2-01) | Planned |
| NFR-004 | Uptime ≥99% business hours | Medium | Availability ASR | Deployment (cross-cutting) | Single-instance PostgreSQL | N/A | Managed PostgreSQL host | Deferred, provider not selected |
| NFR-005 | Usable by low digital-literacy users | Medium | Usability ASR | Request Submission Module (UI) | N/A | N/A | Frontend framework | Deferred |
| NFR-006 | 100% auditable status changes | High | Primary ASR, drove ED-007 & ED-008 | Request Status Module | StatusHistory (append-only, Sec.6) | State Pattern (ED-007) + Observer Pattern (ED-008, audit listener) | Spring Boot + JPA @Transactional | Design translated; coding to begin |
| NFR-007 | Operating cost within near-zero-cost constraint | High | Cost constraint | Deployment (cross-cutting) | N/A | N/A | Free-tier PostgreSQL + free-tier host, provider TBD | Deferred |

RTM v2.0 — Part B: Verification Evidence, Status & ADR/Risk Reference (same ID order as Part A)

| ID | Verification Evidence | Status | ADR / Risk Ref |
| --- | --- | --- | --- |
| FR-001 | Planned | Architecture/ Tech decided, Impl. planned | ADR-M2-01 |
| FR-002 | Planned | Architecture/ Tech decided | ADR-M2-01; DEC-01 |
| FR-003 | Planned | Design decided, Impl. planned | ED-007; ADR-M2-01 |
| FR-004 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-005 | Planned | Design decided, Impl. planned | ED-008; ED-007 |
| FR-006 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-007 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-008 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-009 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-010 | Unit tests planned per state's valid/invalid transitions [TODO: test class link] | In Development | ED-007; ADR-M2-01 |
| FR-011 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-012 | Planned | Design decided, Impl. planned | ED-007 |
| FR-013 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-014 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-015 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| FR-016 | Planned | Architecture/ Tech decided | ADR-M2-01 |
| NFR-001 | Load test planned (50 VUs, Sec.NFR-001) | Architecture decided | ADR-M2-01 |
| NFR-002 | Automated uniqueness test planned (100k refs) | Architecture/ Tech decided | ADR-M2-01 |
| NFR-003 | Independent access-control review planned | Architecture/ Tech decided | ADR-M2-01 |
| NFR-004 | Uptime monitoring report (post-deployment) | Deferred | Risk R-009 |
| NFR-005 | Usability test session planned | Deferred, frontend | N/A |
| NFR-006 | Audit-log completeness query planned [TODO: link] | In Development | ED-007; ED-008; ADR-M2-01 |
| NFR-007 | Billing dashboard check (post-deployment) | Deferred | Risk R-009; CO-03 |

# 13. Initial Design Decision

Requirements Addressed: FR-005 (notify requester when a request is accepted, rejected, updated or completed) and NFR-006 (100% of status transitions logged with timestamp and actors).

Design Problem:

When a status transition completes (validated by the State Pattern, ED-007), at least 2 independent concerns must react to this: 1. The requestor must be notified (FR-005), and 2. An immutable audit entry must be written (NFR-006). If StatusTransitionService call NotificationService and AuditLogService directly then every future consumer of a status change requires changing that same service again. This tightly couples an unrelated set of responsibilities to one class and is the exact mechanism behind Risk R-010 (inconsistent enforcement if a transition path is added without updating every downstream concern).

Alternatives:

- A. Direct method calling (no pattern): StatusTransitionService calls NotificationService and AuditLogService explicitly. Simplest to read but couples the transition logic to every downstream concern which then violates the Open/ Closed Principle.

- B. Mediator Pattern: A central coordinator object that knows about StatusTransitionService and its dependents which then arbitrates between them as needed. This process reduces peer-to-peer coupling, however for CivicConnect’s small size, such a fix is disproportionate for the actual problem size that it faces.

- C. Observer Pattern: The subject (ServiceRequest/ StatusTransitionService) publishes a StatusChangedEvent when a transition completes then NotificationService and AuditLogService will each independently subscribe and react to this event with no direct reference to one another made (Refactoring Guru, 2014; Gamma, et al., 1994).

Final Decision:

Apply the Observer Pattern: When StatusTransitionService completes a valid transition it will publish a StatusChangedEvent (requestID, previousStatus, newStatus, actor, timestamp). NotificationService and AuditLogService will each register as independent observers and react without StatusTransitionService knowing that they exist.

Why it fits CivicConnect:

- It satisfies FR-005 without hard-coding notification logic directly into all the transition services.

- Satisfies NFR-006 by giving the audit write a single trigger point (every valid transition publishes solely one event) instead of a manually-repeated call per feature. This reduces Risk R-010.

- Works well with ED-007: The State Pattern decides if a transition is allowed while the Observer Pattern decides what happens after a transition in accepted.

Benefits and Trade-offs:

Benefit: Decoupling will ensure that StatusTransitionService has no knowledge of notification/ audit logic, single-responsibility, each listener being unit-testable with the pattern extending to the “requestor satisfaction survey” future scope item without it being able to interact with the transition service.

Trade-off: StatusTransitionService alone will no longer show what happens after a transition meaning there is an additional layer of indirection while a developer must also check the list of registered listeners. This can be mitigated by using Spring’s explicit ApplicationEventPublisher mechanism and documenting the event flow in the ReadMe.

Affected Components:

- StatusTransitionService: Publishes StatusChangedEvent after a valid transition (subject to ED-007).

- StatusChangedEvent: Event payload (requestID, previousStatus, newStatus, actor, timestamp).

- NotificationService: Observer that implements FR-005.

- AuditLogService: Observer that implements FR-006 by writing StatusHistory.

# 14. End-to-End Traceability Demonstration

The following demonstrates one full path from requirement to implementation and verification evidence. FR-010 is used as it is a requirement with the most mature engineering chain to date.

| Stage | Evidence |
| --- | --- |
| Requirement | FR-010: Staff may only move a request through a controlled set of valid status transitions. |
| ASR / Constraint | NFR-006 (100% of transitions auditable) is the primary quality driver; Risk R-010 (inconsistent enforcement if the pattern is only partially applied) is the constraint being actively managed. |
| Architecture Responsibility | Request Status Module, within the layered controller/ service/ repository architecture selected in ADR-M2-01. |
| Data Decision | ServiceRequest.status and the StatusHistory table, written atomically inside a single @Transactional boundary. |
| Design / Interface Decision | State Pattern (ED-007) — ServiceRequestStatus interface + concrete state classes (SubmittedState, AssignedState, InProgressState, ResolvedState, ClosedState). |
| Technology / ADR | Java 21, Spring Boot 3.x, Spring Data JPA, PostgreSQL 15+ |
| Application Artefact | To be done in Milestone 3 as Team is learning new Technology |
| Initial Verification | User makes a request -> System assigns staff member to request ->Status of Request is set to “In Progress” -> Staff member resolves request -> Request is closed. Error handling if any step is skipped, error must be thrown to server and handled by admin before any progressive steps can be accomplished. |

# 15. Application/ Technical Documentation for README

### CivicConnect — Community Service Request Management Platform (SEN381, Team "Git Gud")

Current implementation status (Milestone 2): Planning Phase

- Architecture, Technology & Initial Design Baseline v2.0 approved.

- Backend stack: Java 21, Spring Boot 3.x, Spring Data JPA, Spring Security, PostgreSQL 15+.

- Data model baselined: User, ServiceRequest, Category, StatusHistory.

- Design patterns applied to the status-transition domain: State Pattern and Observer Pattern.

Prerequisites

- JDK 21

- Maven 3.9+

- PostgreSQL 15+ (local, or a free-tier managed instance).

Setup & run

- Clone the repository: git clone https://github.com/Nicholas005/SEN381-Project-CivicConnect

- Configure database connection via environment variables or an untracked local application-local.properties (never commit real credentials — see .gitignore)

- Build: mvn clean install

- Run: mvn spring-boot:run

Repository Structure:

- /docs/PED — Project Engineering Document, RTM, ADRs, Risk Register

- /src/main/java/.../request: Request Submission & Queue modules (FR-001–FR-004, FR-006–FR-009)

- /src/main/java/.../status: Request Status module, State Pattern ED-007 (FR-010, FR-003)

- /src/main/java/.../notification: Notification module, Observer Pattern ED-008 (FR-005)

- /src/main/java/.../audit: Audit module, Observer Pattern ED-008 (NFR-006)

- /src/main/java/.../reporting: Reporting module (FR-013–FR-016)

- /src/main/java/.../auth: Auth/RBAC module, Spring Security (FR-006, NFR-003)

- /src/test/java/...: automated tests

- /.github/workflows: CI checks

Project layout is subject to change

Known limitations / TODOs as of Milestone 2

- Frontend framework not yet finalised (owner: Web App Lead).

- Hosting/deployment provider not yet selected (Risk R-009).

- Team members still learning new technologies.

# 16. Architecture, Technology and Initial Design Baseline

As RTM/baseline coordinator (same role held for the M1 baseline sign-off), this section records what the M2 Architecture, Technology & Initial Design Baseline consists of, what remains open, using the Master Brief Appendix D template.

## 16.1 What Is Included in Baseline v2.0

- Architecturally significant requirements & quality drivers (PED: team section, cross-referenced in RTM v2.0 above).

- Architecture decision & diagrams (PED: team section).

- Data & Persistence Baseline: Sec.6 (User, ServiceRequest, Category, StatusHistory; PostgreSQL via Spring Data JPA).

- Technology-Stack Decision: ADR-M2-01 (Java 21/ Spring Boot 3.x/ Spring Data JPA/ Spring Security/ PostgreSQL 15+).

- Design Decision 1: ED-007, State Pattern for controlled status transitions (FR-010).

- Design Decision 2: ED-008, Observer Pattern for status-change notification & audit trail (FR-005, NFR-006).

- RTM v2.0: evolved with ASR, architecture, data, design, technology, implementation and verification columns.

## 16.2 Known Open/ Deferred Decisions (not yet part of the baseline)

- Frontend framework: owned by the Web App Lead; RTM rows NFR-005 and the UI portion of FR-001–FR-016 marked Deferred until this is decided.

- Hosting/ deployment provider: Risk R-009; RTM rows NFR-004 and NFR-007 marked Deferred until a specific provider's free-tier limits are documented.

- Detailed RBAC model: per Engineering Decision Log ED-005, deferred from M1; to be finalised as an ADR once access-control requirements are further detailed.

- Any external/API integration: none has yet reached a meaningful boundary; recorded as a forward engineering consideration per M2 brief Sec.5.7 rather than invented.

# 17. GitHub Repository & Governance

## 17.1 Repository Details

| Item | Detail |
| --- | --- |
| Repository URL | https://github.com/Nicholas005/SEN381-Project-CivicConnect |
| Owner / Organisation | Nicholas005 |
| Visibility | Public |
| Default branch | main |
| Repository structure | -readme ¦ ¦ -SEN381_Project_Milestone1 |

## 17.2 Governance Controls Checklist

- Repository created and all team members added

- Main branch protected - no direct commits for substantive changes

- Pull Request template in place

- Minimum two reviewer approvals required, self-approval disabled

- Issue/task board set up and linked to work items

- No secrets/credentials committed (.gitignore configured)

# 18. AI Usage Register

| Date | Student | Tool | Engineering Task | AI Contribution | Verification | Decision | Issues Found |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 07/09/2026 | Rivan Maritz | Claude AI | Creating the word document | Created the template to be used for this word document | Verified by Nicholas Armin Vronka | Template to be used | Some areas had comments on what must be added. They were removed. |
| 08/09/2026 | Michiel Coenraad TerBlanche | Claude AI | Used to help go through the CivicConnect Master Brief | Helped me find and put together the information needed for my part that was in the document |  | Found it helpful and used it to go through the document | Made some formatting mistakes and corrected them |
| 09/08/2026 | Nicholas Armin Vronka | Claude AI | Used to summarise the CivicConnect Master brief for Milestone 1. | Helped me remove sections that were not my assigned work in this document. |  | Implemented the suggestions once they had been double checked by myself and were relevant to the topic covered. | Trimmed false information given and corrected sections that were not relevant to the Milestone 1 requirements. |
| 23/09/2026 | Nicholas Armin Vronka | Claude AI | README drafting as well as workshopping ideas for the updated RTM. | Produced a draft structure for the RTM. |  | Implemented an edited version of the draft given to ensure. | Draft lacked some details that needed to be added. |
| 24/09/2026 | Michiel Coenraad TerBlanche | Claude AI | Made a draft of the M1 evolution Requirements, ASR, Architecture decisions and Deployment compatibility | It created a Draft for the requested work |  | Implemented an edited version of the draft | Draft was mostly correct but had some minor hallucinations and missing detail |
| 25/09/2026 | Michiel Coenraad TerBlanche | Claude AI | Make diagrams for Architecture Decision & Diagrams and Deployment Compatibility | Made the diagrams since I didn’t like how mine looked | Made sure that the diagrams where correct to the work | I kept the diagrams since it looked better than what I could make | No real issues were found |
| 16/10/2026 | Michiel Coenraad TerBlanche | Claude AI | Merged the Java-Backend, database/Docker resources and frontend into one project (CC-03, CC-05, D-04). | JPA adapters, UUID keys, login with signed tokens and role checks, a request_comments migration, frontend wired to the real API, Docker setup. | Ran the merged project and confirmed it worked. The AI compiled the backend and ran the business-logic tests in its own environment; it did not run Maven. | Accepted after the student ran it | No Maven or CI run was possible, so the Spring wiring was verified by running the project, not by the AI. |
| 17/10/2026 | Nicholas Armin Vronka | Claude AI | Automated tests and CI for M3 (A-01 to A-05, E-01 to E-05, ArchUnit, P-01, workflows). | 33 integration tests, 4 architecture rules, 5 browser tests, 37 frontend unit tests, k6 script, GitHub Actions workflows, traceability file. | 56 of 60 unit tests and 37 Vitest tests passed; 5 Playwright tests passed 30 times on the mock API; the SQL the integration tests rely on was checked on a real PostgreSQL. | Kept; to be run in CI by the team | The 33 integration tests, the ArchUnit rules, the workflows, the Docker build and the k6 script were not executed by the AI. A-02 expectation differs from the PED (D-08). |
| 18/10/2026 | Rivan Maritz | Claude AI | Gap analysis of PED v3.0 against the Final Project brief; draft of PED v4.0 Sections 42 to 53. | Scope table, Scope Completion Percentage calculation, final RTM, deployment decision draft, reflection draft, outstanding list. | Statuses were taken from the repository and test reports. Nothing was entered for CI, commit hash, P-01 or staging; those are highlighted. | Draft for team review | The team must confirm every status, the percentage and the go-live decision from its own evidence before submission. |

# 19. Initial Deployment / Operational Considerations

| Consideration | Notes |
| --- | --- |
| Candidate hosting platforms | Under consideration: [Azure App Service / Render / Railway] – free tiers exist but with cold-start and resource limitations that need further research before Milestone 2. |
| Environment strategy | Development and a single hosted environment are expected initially; a distinct staging environment will likely be introduced ahead of Milestone 3’s controlled release requirements. |
| Data / privacy considerations | Service requests may contain personal information (e.g. requester contact details). Access control and data handling will be defined formally as part of the Security Engineering Standard at later milestones; flagged here as an early awareness item, per NFR-003. |
| Cost | Team intends to remain within free-tier limits during the academic period (see NFR-007 and CO-03); realistic operational cost beyond the free tier has not yet been researched and will be revisited at Milestone 2. |
| Status of this section | Provisional. No deployment or hosting decision has been made at Milestone 1; this section records early thinking only, to be formalised with a justified decision (ADR) at Milestone 2. |

# 20. M1 Baseline Review & Requirements Evolution

## 20.1 Review scope and outcome

The 16 functional requirements, 7 non-functional requirements, 6 assumptions, 7 constraints and the scope baseline were read against the M2 evidence: the data model (Section 6), ADR-M2-01, the State and Observer decisions (ED-007, ED-008) and the hosting limits found in Section 23. The test applied to each acceptance criterion was simple: can it be implemented and verified with the decisions made so far?

- No requirement was removed and no in-scope item was dropped.

- Six items cannot be implemented or measured as written and need a clarification or change (CR-01 to CR-06).

- None of the CRs adds a new user-facing capability. CR-04 turns an unstated exclusion (email/SMS) into an explicit one.

- Four assumptions and two constraints are added (Section 20.4), and two existing assumptions are qualified.

## 20.2 Change request register

| CR | M1 Baseline Text | Finding From M2 Evidence | Proposed M2 Wording/acceptance | Type and Affected Artefacts | Status |
| --- | --- | --- | --- | --- | --- |
| CR-01 | NFR-004: >= 99% uptime in "defined business hours". NFR-001: 95th percentile <= 3 s at 50 users. | Business hours were never defined, so NFR-004 cannot be measured. The candidate free hosts sleep after 15 minutes idle and take about a minute to wake (Section 23.1). Counting that wake-up would fail both targets on the first request after any idle gap. | NFR-004: business hours are 07:00 to 18:00 SAST, Monday to Friday. Availability is the share of scheduled health checks in that window that succeed, >= 99% per calendar month. NFR-001: measured against a warm instance (one that answered a request in the previous 5 minutes). Cold-start delay is tracked under NFR-004 and R-011. | Clarification (targets unchanged). Affects: Sec 3.2, RTM, ASR-05, R-011, Sec 23. | Proposed |
| CR-02 | FR-014: overdue means "an assigned overdue threshold per category". | Category (Section 6) has only id, name and active. Nothing stores a per-category threshold, so overdue requests cannot be calculated. | FR-014 wording unchanged. Add Category.overdue_after_hours (integer, > 0, NOT NULL). Acceptance is unchanged: requests older than the threshold for their category are marked overdue. | Data-model change. Affects: Sec 6 and ERD, RTM FR-014. | Proposed (Data lead) |
| CR-03 | FR-005: notify when a request is "accepted, rejected, updated or completed". ED-007: five states (Submitted, Assigned, In Progress, Resolved, Closed). | No state represents a rejected request, so the "rejected" message in FR-005 has nothing to trigger it. | Add a terminal state Rejected, reachable only from Submitted by authorised staff, with a mandatory reason stored in StatusHistory.comment. Acceptance: given a Submitted request, when staff reject it with a reason, then status is Rejected, the requester sees the reason and every further transition is refused. | Requirement clarification and design change (ED-007 gains RejectedState). Affects: FR-005, FR-010, Sec 8, RTM, state tests. | Proposed |
| CR-04 | FR-005: "notify the requester with meaningful feedback". The acceptance criterion is an in-app view update within 1 minute. | "Notify" can be read as email or SMS. That needs an outbound mail service, credentials and possibly cost, which conflicts with NFR-007 and CO-05. | FR-005 is satisfied in-app only (status message in the requester's view, stored as a notification). Email, SMS and push are added to Section 2.2 as out of scope and stay in Future scope. | Clarification (scope made explicit). Affects: Sec 2.2, FR-005, Notification module, Sec 23.3. | Proposed |
| CR-05 | FR-012: "resolve or close". Acceptance covers Resolved only and says the request becomes read-only. | ED-007 has both Resolved and Closed, but nothing says who moves a request from Resolved to Closed or whether FR-011 comments are still allowed after Resolved. | Resolve: authorised staff set Resolved with a resolution note. The request is then read-only (no edits or comments). Close: authorised staff or a manager move Resolved to Closed. Closed is terminal. Acceptance tests both transitions and that a comment after Resolved is refused. | Clarification. Affects: FR-011, FR-012, ED-007, tests. | Proposed |
| CR-06 | FR-006: staff see only requests "within their authorised category/team". | User holds only a role (Section 6). Nothing records which categories or teams a staff member may see, so FR-006 cannot be built or tested. | FR-006 wording unchanged. Add join table user_category (user_id, category_id, unique pair, both foreign keys). "Team" is treated as a set of categories until the detailed RBAC ADR (ED-005) decides otherwise. | Data-model change and input to the RBAC ADR. Affects: Sec 6, FR-006, NFR-003, ASR-02, ED-005. | Proposed (Data lead) |

## 20.3 Data-model delta (input to Section 6)

| Change | Reason | Source | Approval |
| --- | --- | --- | --- |
| category.overdue_after_hours | Lets management see overdue requests per category (FR-014). | CR-02 | Rejected |
| user_category (user_id, category_id) | Records which categories a staff member may see (FR-006, NFR-003). | CR-06 | Approved |
| service_requests.version | Optimistic-lock counter so two staff acting on the same request cannot overwrite each other (ASR-03). | ASR-03 | Approved |
| notifications (id, request_id, recipient_id, message, created_at, read_at) | Stores the in-app status message the requester sees (FR-005). | CR-04 | Rejected |
| service_requests.status accepts REJECTED | Supports the new terminal state (FR-005, FR-010). | CR-03 | Rejected |

## 20.4 Assumptions and constraints review

| ID | Statement | Status | Note / risk if invalid |
| --- | --- | --- | --- |
| AS-04 | Stack is installable on the BC Desktop / available development environment. | Still open | Java 21, Maven 3.9+ and PostgreSQL 15+ must be confirmed on the BC Desktop image and the result recorded in the README. Docker is optional locally because the host builds the image remotely. |
| AS-05 | A free or low-cost tier gives enough capacity for the academic year. | Qualified | Holds for the application tier. For the database tier it depends on the provider: Render's free PostgreSQL expires 30 days after creation, while a permanent free tier is needed (Section 23.1). |
| AS-07 (new) | Hosting is a container-based PaaS free tier, deployed from the GitHub repository. | New | If invalid, the deferred hosting decision (Section 23.6) reopens and the demo may have to run locally. |
| AS-08 (new) | The hosted environment holds synthetic test data only. | New | If invalid, real personal information would need a POPIA hosting and cross-border assessment that is outside M2 (R-016). |
| AS-09 (new) | Business hours are 07:00 to 18:00 SAST, Monday to Friday. | New | Needed to measure NFR-004. Sponsor to confirm (CR-01). |
| AS-10 (new) | Data volume for the academic period stays far below 0.5 GB. | New | Order-of-magnitude estimate: about 10,000 requests with a few history rows each is tens of MB. If wrong, the free database compute suspends at its cap (R-012). |
| CO-08 (new) | The repository is public (Section 17.1): no secrets or real personal data may ever be committed. | New | Drives environment-variable configuration, secret scanning and a review checklist item (R-013). |
| CO-09 (new) | Free-tier terms belong to third-party providers and can change without notice. | New | Deployment must stay portable (container image plus environment configuration) so that changing provider is a configuration change (R-015). |

## 20.5 Effect on the baseline and the RTM

- The M1 wording in Sections 3 and 4 stays visible. Where a CR is approved, the new wording carries the CR reference and the RTM row shows status "Changed".

- RTM v2.0 rows to update on approval: FR-005, FR-006, FR-010, FR-012, FR-014, NFR-001 and NFR-004.

- Section 24 records "no material changes identified" for the M1 scope. That was true when it was signed. If CR-03 or CR-06 is approved, the sign-off must be renewed and the change noted in Document Control.

- The risks raised by this review are logged as R-011 to R-016 (Section 23.5).

# 21. Architecturally Significant Requirements & Quality Drivers

An architecturally significant requirement (ASR) is one that shapes the structure of the system and would be costly to retrofit. Every NFR and constraint was tested against one question: would a different architecture, data or deployment decision be needed to meet it? Five qualify. The two that do not are recorded in Section 21.3 so the list is not padded.

## 21.1 ASR register

| ID | Driver and evidence | Measurable scenario | Influence on architecture, data, technology and design | Tension / risk |
| --- | --- | --- | --- | --- |
| ASR-01 (primary) | Auditability and lifecycle integrity NFR-006, FR-010, FR-012. Management needs accountable, auditable status history (stakeholder analysis, influence H). Risk R-010. | Given any status-change attempt: a valid one saves the new status and its audit row together (100%), an invalid one changes nothing. Measure: audit query shows a gap-free ordered history, a fault test that forces the audit insert to fail leaves the status unchanged. | One ACID transaction rules out splitting status and audit across services (ADR-M2-02). A single write path for status (status module only). State pattern decides validity (ED-007). The audit listener runs synchronously inside the transaction (Figure 22-2). Append-only status_history. Relational store (Section 6). | Observer decoupling (ED-008) versus atomicity. Resolved by an in-transaction audit listener. |
| ASR-02 | Confidentiality and access control NFR-003, FR-006, CO-05. Requesters expect privacy, management wants detail (stakeholder analysis). Risks R-003, R-008. | Given an unauthenticated user, or a user outside a record's scope, when they request that record, then they get 401 or 403 and no personal data appears in the response or the logs. Measure: every endpoint has a role and scope rule (default-deny) with automated per-role tests; independent review finds no personal fields in public endpoints or logs. | Auth/RBAC module and a default-deny API boundary. Authorisation is re-checked in the service layer, not only in controllers. Category scope through user_category (CR-06). No personal data in logs. Secrets kept outside code (Section 23.3). HTTPS only. | Team is new to Spring Security (R-008). Detailed RBAC model still deferred (ED-005). |
| ASR-03 | Data integrity and concurrency NFR-002, FR-002, FR-012. The sponsor needs one trustworthy record per request (problem statement). | 100,000 generated references contain zero duplicates. Two staff changing the same request at the same moment: exactly one succeeds and the other receives a conflict (HTTP 409). A resolved request refuses edits. Measure: uniqueness test, two-thread update test. | Database constraints as the last line of defence (UNIQUE, foreign keys, NOT NULL, status check). Optimistic locking through service_requests.version (Section 20.3). Transactions at service level. Reference generation (sequence-based or random with a UNIQUE retry) is chosen at implementation, the UNIQUE constraint is mandatory either way. | Adds a column and a conflict path the frontend must show clearly. |
| ASR-04 | Cost containment NFR-007, CO-03, AS-05. Sponsor influence is H and expects near-zero cost. | For the whole academic period, hosting, database and tooling stay inside the providers' documented free quotas. Measure: usage and billing dashboards show no charge and documented quota headroom. | One deployable and one database. No message broker, cache or extra managed service. Free-tier PaaS plus free PostgreSQL (Section 23). Rules out multi-service architectures. A portable Docker image limits provider lock-in. | Directly opposes ASR-05 (free tiers sleep and have caps). See Section 21.4. |
| ASR-05 | Availability and restart resilience NFR-004, and the warm-instance rule for NFR-001 (CR-01). Staff check the platform daily (AS-02). | During business hours (AS-09), >= 99% of scheduled health checks succeed each month. After the service sleeps or restarts, the next request works with no lost login state or data. Measure: monitoring report; a restart test (stop the container, then request). Reference: 1% of about 242 business hours a month is about 2.4 hours of allowed downtime. | Stateless application tier: no in-memory sessions (signed tokens or database-backed sessions, decided in the RBAC ADR). No files kept on disk because the host filesystem is ephemeral. Lean start-up configuration. A health endpoint for the host. Single-instance database accepted as a known single point of failure (Section 6). | Cost (ASR-04) and cold starts on the free tier (R-011). |

## 21.2 Priority order

Team judgement, to be confirmed with the sponsor: ASR-01 > ASR-02 > ASR-03 > ASR-04 > ASR-05. Correctness and confidentiality of request data outrank cost, and cost outranks availability, because a slow first request during a demo is recoverable but a missing audit row or an exposed record is not.

## 21.3 Considered and not treated as architecture drivers

- NFR-005 (usability for low digital literacy) is a secondary driver. It constrains the frontend (simple, responsive forms) but not the backend structure. It is the reason frontend delivery stays open in Section 16.2, and the plain REST/JSON boundary works with either frontend approach.

- NFR-001 (submission within 3 seconds at 50 users) is not treated as architecture-significant. It should be within reach of a single Spring Boot instance on a relational store, and will be confirmed by the M3 load test. Its real risk is the free host's 0.1 CPU and cold start, which is captured under ASR-05 and R-011.

## 21.4 Tensions and how they are resolved

| Tension | Why it arises | Resolution |
| --- | --- | --- |
| ASR-01 versus ED-008 (decoupling) | Observer keeps audit and notification independent of the transition service, but NFR-006 needs the audit row to exist if and only if the status change committed. | Audit listener is synchronous and inside the transaction. Notification listener runs after commit. Recorded in ADR-M2-02. |
| ASR-04 versus ASR-05 (cost versus availability) | Free tiers sleep, have small resources and can suspend at quota. | Cost wins for the academic period. Availability is measured only in business hours on a warm instance (CR-01). Contingency if a demo needs it: a paid always-on instance or a local demo (R-011). |
| ASR-02 versus reporting detail | Management wants fine-grained detail but requesters expect data minimisation (stakeholder analysis). | Reporting returns aggregates and request references, never requester personal fields. |

## 21.5 RTM link (input to the "ASR / Quality Driver" column)

| Driver | Requirements | Suggested RTM cell text |
| --- | --- | --- |
| ASR-01 | FR-005, FR-010, FR-011, FR-012, NFR-006 | Auditability and lifecycle integrity (ASR-01) |
| ASR-02 | FR-006, NFR-003 | Confidentiality and access control (ASR-02) |
| ASR-03 | FR-001, FR-002, FR-012, NFR-002 | Data integrity and concurrency (ASR-03) |
| ASR-04 | NFR-007 | Cost containment (ASR-04) |
| ASR-05 | NFR-004, NFR-001 (warm-instance rule) | Availability and restart resilience (ASR-05) |
| Secondary | NFR-005 | Usability (secondary driver, frontend decision) |
| None | FR-003, FR-004, FR-007, FR-008, FR-009, FR-013 to FR-016 | Standard functionality, not architecture-significant |

# 22. Architecture Decision & Diagrams (ADR-M2-02)

ADR-M2-01 fixed the technology (Java 21, Spring Boot, PostgreSQL). This section decides how the system is structured. It answers to the ASRs in Section 21 and to the constraints of three people, one semester and near-zero cost.

## 22.1 Alternatives considered

| Option | What it is | Strengths | Weaknesses against CivicConnect | Verdict |
| --- | --- | --- | --- | --- |
| A. Layered monolith (package-by-layer) | One deployable. Shared controller, service and repository packages used by every feature. | Simplest. One ACID boundary (ASR-01). Cheapest (ASR-04). | Nothing stops any service from writing any table, so the status and audit rule (R-010) is only a convention. Feature code is scattered across layers, which makes it hard to split between three people and to map to RTM modules. | Rejected: every strength is kept by B. |
| B. Modular monolith (package-by-feature) | One deployable and one database. Feature modules, each layered inside. Modules talk through a public service interface or an event. | Keeps A's single transaction, cost and simplicity. Explicit data ownership per module. RTM modules map one-to-one to packages. Boundary rules can be tested automatically. A module can be extracted later if evidence demands. | Needs discipline (no cross-module repository access). A little more up-front structure than A. Still one failure domain. | Selected |
| C. Microservices | Separate services, for example request, status and audit, notification, reporting and auth. | Independent deploy and scale. Strong isolation. | A status change and its audit row would span services, needing a saga or outbox to keep NFR-006 at 100% (ASR-01). Five or more deployables and databases on free tiers (ASR-04). Larger network attack surface (ASR-02). Operational load beyond three students (CO-01). | Rejected: no driver justifies the complexity. |
| D. Serverless functions with a managed database | One function per endpoint, managed PostgreSQL. | Scale-to-zero cost. No servers to manage. | Java cold starts and database connection limits on free tiers. Authorisation logic spread across many functions (ASR-02). Departs from ADR-M2-01 and from what the team knows. | Rejected. |

## 22.2 Selected architecture: modules and diagrams

The logical view (Figure 22-1) shows responsibilities and boundaries. It is not a deployment diagram: the physical nodes are in Figure 23-1. Figure 22-2 shows the one interaction that carries the primary ASR.

Figure 22-1: Logical architecture (modular monolith). Module names follow the RTM; packages follow the README.

| Module (RTM name) | Package | Responsibility | Owns / writes | Public interface | May depend on |
| --- | --- | --- | --- | --- | --- |
| Auth / RBAC | auth | Authenticates users. Role and category-scope checks. | users, user_category | Access-check service | None |
| Request submission and queue | request | Creates requests with a controlled category. Lists, filters and shows detail. | service_requests (create, read), categories | RequestService | auth |
| Assignment | assignment | Decides who may assign or accept. Triggers the Submitted to Assigned transition. | No table of its own | AssignmentService | auth, status |
| Request status (with resolution) | status | Performs every status change through the State objects. Records resolution notes. Publishes StatusChangedEvent. | Status and assignee columns of service_requests (write) | StatusTransitionService, StatusChangedEvent | request, auth |
| Audit | audit | Writes the append-only history from each event. | status_history (insert only) | None (listener) | status (event type) |
| Notification | notification | Stores and serves in-app messages from each event. | notifications | NotificationQueryService | status (event type), auth |
| Reporting | reporting | Read-only counts, overdue list and average resolution time. | None (read-only queries) | ReportingService | request, auth |

Figure 22-2: A status change. The audit write is inside the transaction, the notification is after commit.

## 22.3 ADR-M2-02: Modular monolith

| Field | Detail |
| --- | --- |
| ADR / Decision Log ID | ADR-M2-02 / ED-009 |
| Status | Proposed (baseline candidate, pending two independent approvals) |
| Date and author | 25/09/2026, Michiel Coenraad TerBlanche (Java App Lead) |
| Related | ADR-M2-01, ED-007, ED-008, ASR-01 to ASR-05, R-010, R-011 |
| Evidence used | ASR analysis (Section 21). Week 2 architecture teaching (cite the module notes). Provider documentation for deployment fit (Section 23.7). No Assignment 2 research was needed for this decision. |

Context

Every status change and its audit record must stay consistent (ASR-01), request data must be protected (ASR-02), hosting must stay on free tiers (ASR-04) and three students must build it in one semester (CO-01, CO-02). The technology is already fixed, so the open question is how to structure the code and the deployable units.

Decision

Build CivicConnect as a modular monolith: one Spring Boot application, one deployable artefact and one PostgreSQL database. Code is organised into the feature modules in Section 22.2, each layered internally (controller, service, repository). Modules interact only through a public service interface or the StatusChangedEvent.

Transaction rule (clarifies ED-008)

StatusTransitionService runs inside one Transactional boundary. The audit listener is synchronous and joins that transaction, so a failed audit insert rolls back the status change. The notification listener runs after commit, so a requester is never told about a change that was rolled back. Reason: an asynchronous or after-commit audit listener would let a status change commit with no audit row and break NFR-006. In Spring, a plain Event Listener runs in the publisher's thread and transaction, while Transactional Event Listener defaults to the after-commit phase.

Consequences

- Positive: one ACID transaction covers the status update and the audit write (ASR-01). One container and one database fit the free tier (ASR-04). The boundary rules make ED-007 and ED-008 enforceable, which reduces R-010. Packages match the RTM modules and the README, and each team member can own modules.

- Negative, accepted: a single failure domain, so one crash or deploy takes everything down (NFR-004 is a business-hours target only). Scaling is all-or-nothing, which is fine at the expected volume. The boundary rules need discipline. Extracting a module later would mean replacing in-process events with messaging and splitting the database.

- Neutral: frontend delivery is unaffected because the boundary is plain REST/JSON.

Enforcement

- Repositories and services are package-private to their module.

- An automated architecture test checks the four boundary rules in Figure 22-1. ArchUnit is the candidate; confirm that its version works with the chosen Spring Boot before adding it. This test is the initial verification evidence for R-010.

- The Pull Request checklist gets one line: no cross-module repository access, and status changes only through StatusTransitionService.

If this decision were reversed

Moving to microservices would change: the deployment direction and cost evidence (Section 23, NFR-007), the data model (a database per service, Section 6), ED-008 (events become messaging with an outbox), every Architecture cell of the RTM, the README structure, and risks R-009 and R-011 (several free instances). Moving to a plain layered monolith would change only the package structure, the boundary tests and the R-010 mitigation.

Follow-up actions

- Add the assignment package to the README repository structure.

- Adopt the module names above in the RTM Architecture column.

- Add a one-line note to ED-008 pointing to the transaction rule.

- Append ED-009 to the Engineering Decision Log (Section 11).

## 22.4 Architecture, technology and deployment kept apart

| Logical structure | Tools that implement it | Where it runs |
| --- | --- | --- |
| Architecture (this section) Modular monolith. Seven modules with data ownership. Event-based reaction to status changes. Transaction rule. Boundary rules. | Technology (ADR-M2-01, Section 23.4) Java 21, Spring Boot, Spring Data JPA, Spring Security, PostgreSQL 15+, Maven. | Physical deployment (Section 23) One container, one managed database and the browser: three nodes that hold all seven logical modules. |

# 23. Deployment Compatibility (M2)

Section 19 recorded early, provisional thinking at M1. It is kept unchanged as history. This section supersedes its hosting, environment and cost rows with a deployment direction, compatibility checks against the M2 decisions, and a list of decisions that are deliberately still open. M2 anticipates deployment; it does not build a pipeline.

## 23.1 Deployment direction (ADR-M2-03 / ED-010)

Status: Proposed. Decision: the direction is one Docker image of the Spring Boot application, run as a single web service on a PaaS free tier, connected over TLS to a managed PostgreSQL instance from a separate provider. Configuration and secrets come from environment variables. Source is in GitHub. Environments are local development plus one hosted demo environment. Staging waits for M3, as Section 19 already expected. The provider is not chosen yet (Section 23.6).

Figure 23-1: Physical deployment direction. Solid boxes are decided; dashed boxes are deferred or candidates.

## Candidates and what the evidence says:

| Candidate | Role | What the evidence says | Fit / open question |
| --- | --- | --- | --- |
| Render free web service | App host | No native Java runtime, so Docker is required. 512 MB RAM and 0.1 CPU. Sleeps after 15 minutes without traffic and takes about a minute to wake. 750 free instance-hours a month. Ephemeral filesystem. | Fits ASR-04. Cold start conflicts with ASR-05 (R-011). One always-on service fits in 750 hours (31 x 24 = 744), but any keep-alive practice must be checked against Render's terms first. |
| Render free PostgreSQL | Database | Free databases expire 30 days after creation. | Rejected for the database: cannot last the academic period (NFR-007, AS-05). |
| Neon Free | Database | Permanent free plan. 0.5 GB per project and 100 compute-hours a month. Compute scales to zero after 5 minutes idle. Hitting a limit suspends compute until the next month. Short restore window (6 hours). | Best current fit for the database. Wake-up delay, the 100-hour cap and supported PostgreSQL version must be tested (R-012). |
| Supabase Free | Database | Reported to pause after about a week idle (third-party source, not yet checked in Supabase's own documentation). | Weaker fit: a term break could pause the database. Verify before considering. |
| Azure App Service (Free) or Railway | App host | Named in Section 19 but not researched. Railway is reported to give a one-time trial credit rather than a permanent free tier (third-party source). | Open: needs first-party research before any choice. |

## 23.2 Are the M2 decisions plausible for this direction?

| Decision | Deployment implication | Verdict |
| --- | --- | --- |
| Modular monolith (ADR-M2-02) | One process in one container, no service-to-service networking. Matches one free web service. | Compatible |
| Java 21 and Spring Boot (ADR-M2-01) | Render has no native Java runtime, so the repository needs a Dockerfile (multi-stage Maven build, then a JRE 21 image). This also keeps the image portable between hosts. | Compatible with a Dockerfile |
| JVM on a 512 MB / 0.1 CPU instance | Slow start-up and memory pressure are likely. Cap the heap through container-aware JVM options, keep dependencies lean and consider lazy initialisation. Measure start-up and first-request time in the spike before committing. | Unverified |
| PostgreSQL 15+ (Section 6) | The managed database must support that version and TLS, and must not expire. Choose a permanent free tier. | Compatible with a Neon-class provider |
| Stateless application (ASR-05) | The host filesystem is ephemeral and the service sleeps, so nothing is kept on disk or in memory between requests. | Compatible |
| In-process events (ED-008) | Events stay inside one instance. Running several instances would need a broker. Not needed at the planned scale. | Compatible at planned scale |
| Schema management | Schema changes are applied by versioned migrations (Flyway or Liquibase, chosen at implementation), not by Hibernate ddl-auto=update on the hosted database. | New rule |
| Backup and recovery (Section 6) | Free tiers offer only a short restore window. A tested export and restore is deferred (Section 23.6). | Accepted limitation |

## 23.3 Configuration, secrets and networking

| Area | Implication | Rule for the team |
| --- | --- | --- |
| Configuration | Environment variables override packaged defaults. Spring profiles: local and hosted. The port comes from the platform's PORT variable (server.port=${PORT:8080}). | No environment-specific value in a committed file. |
| Secrets | Database URL and credentials, and the authentication signing secret. Hosted: platform secret store. Local: an untracked application-local.properties. | Never commit a secret. The repository is public (CO-08). Enable secret scanning and push protection if available. Rotate immediately if one leaks (R-013). |
| Database connection | The database is external, over the public internet. | Require TLS in the JDBC URL. Use a least-privilege database user. Keep the connection pool small. Set the size from the provider's documented limit (R-012). |
| Inbound traffic | HTTPS only, with TLS ended by the platform. | Redirect HTTP to HTTPS. Expose only the health endpoint from actuator, keep every other actuator endpoint closed (ASR-02). |
| Cross-origin | Depends on the deferred frontend choice. | If the frontend is on another origin, use an explicit allow-list (CORS_ALLOWED_ORIGIN), never a wildcard. If it is bundled in the JAR, no CORS is needed. |
| Outbound traffic | None in the baseline (CR-04: no email or SMS). | No outbound credentials to manage. |
| Logging and data | Logs go to standard output, which the platform captures. | No personal data in logs (NFR-003). Synthetic data only in the hosted environment (AS-08). Record the hosting region, it may be outside South Africa, so real personal data would need a POPIA assessment first (R-016). |
| State | The database is the only store of state. | No files on disk, no in-memory sessions. |
| Time | Status timestamps, audit entries and overdue checks all depend on time. | Store timestamps in UTC (timestamptz) and display in SAST. |

## 23.4 Versions and platform support (proposed amendment ADR-M2-01-A1)

Finding. ADR-M2-01 names "Spring Boot 3.x". Spring's own announcement for 3.5.16 (25 June 2026) says it is the last open-source release of the 3.x line and tells users to move to 4.0.x or 4.1.x. Spring Boot 3.x therefore receives no free security fixes from 1 July 2026. A third-party summary of Spring's support table puts the end of open-source support for 4.0.x at December 2026 and for 4.1.x at July 2027. Confirm both dates on Spring's support page before pinning.

| Option | For | Against |
| --- | --- | --- |
| Spring Boot 4.1.x (proposed) | Supported through the end of the project. No application code exists yet, so there is no migration cost. | Newer major version (Spring Framework 7, Jackson 3, Spring Security 7). Most tutorials still show 3.x, which raises R-008. |
| Spring Boot 4.0.x | Supported until about December 2026, which is close to the final milestone. | Same learning cost as 4.1.x with a shorter support window. Not recommended. |
| Stay on Spring Boot 3.5.x | Familiar tutorials. | No open-source patches. Weakens the "security ecosystem" reason for choosing Spring in ADR-M2-01, for an application that holds personal data (ASR-02). |

Proposed decision: use Spring Boot 4.1.x (latest patch) on Java 21 LTS with Maven 3.9+ and PostgreSQL 15+. Record the exact versions in pom.xml and the README. Run a short spike on Spring Security and Spring Data JPA under 4.x before FR-006 work starts. If 4.x blocks progress, fall back to 3.5.16 with a written risk acceptance (R-014). The original ADR-M2-01 text is retained and is superseded only when this amendment is approved.

## 23.5 Risks raised (proposed additions to the Risk Register)

| ID | Risk | Priority | Mitigation | Contingency | Owner (proposed) |
| --- | --- | --- | --- | --- | --- |
| R-011 | Free web service cold start and 0.1 CPU / 512 MB make the first request slow, missing NFR-001 and NFR-004 in a demo. | High | Warm-instance measurement rule (CR-01). Spike to measure start-up. Lean JVM settings. Warm the service before demos. Check whether business-hours health checks are allowed by the host. | Paid always-on instance for demo weeks, or run the demo locally with Docker. | Michiel |
| R-012 | Free database limits (30-day expiry, 0.5 GB, 100 compute-hours, pausing) cause an outage or data loss. Extends R-009. | High | Use a permanent free tier. Document quotas. Watch usage. Keep migrations and a seed script in the repository. | Rebuild the database from migrations and seed data, or use local PostgreSQL. | Rivan |
| R-013 | A secret is committed to the public repository (CO-08). | High | Environment variables. .gitignore. Secret scanning and push protection. PR checklist line. Review configuration diffs. | Rotate credentials immediately. Purge history if needed. | Rivan |
| R-014 | Spring Boot 3.x is unsupported if kept, or Boot 4.x slows the team down if adopted. | Medium | Decide ADR-M2-01-A1 this week. Pin versions. Enable dependency alerts on the repository. | Fall back to 3.5.16 with a written risk acceptance. | Michiel |
| R-015 | A provider changes its free-tier terms before M4. | Medium | Portable Docker image and environment-only configuration. One deployment note per provider. | Swap provider, or demo locally. | Michiel |
| R-016 | Personal data is placed in the hosted demo without a compliance assessment. | Medium | AS-08: synthetic data only. Test-data generator. Review checklist. | Purge, rotate secrets, tell the lecturer. | Rivan |

## 23.6 Deliberately deferred decisions and the evidence still needed

| Decision | Why deferred | Evidence needed before deciding | Target |
| --- | --- | --- | --- |
| Hosting provider for app and database | Free-tier claims are not yet proven in practice. | A walking-skeleton spike on the shortlisted host: health endpoint, one migration and one query. Record start-up time, memory use, connection limit and region, and compare with the provider documentation. | Before M3 starts |
| Frontend delivery (bundled or separate host) | Web App Lead has not chosen a framework (Section 16.2). | Frontend decision, plus its CORS and token or cookie implications. | With the frontend ADR |
| Authentication mechanism (signed tokens or database sessions) | RBAC ADR deferred (ED-005). | RBAC ADR and a restart test proving ASR-05. | Before FR-006 is built |
| Backup and restore | Free tiers give limited backups. | Provider backup terms and one tested restore from an export. | Before the M3 demo |
| Staging environment and automated deploy | Belongs to M3 controlled release. CI adoption is progressive. | CI decision from the Week 4 SCM/CI work and the cost of a second environment on a free tier. | M3 |
| Monitoring for NFR-004 | No hosted environment yet. | Chosen uptime monitor and an approved business-hours definition (CR-01). | First hosted deploy |
| Hosting region and data residency | Provider not chosen. | Region list of the chosen provider and POPIA considerations if any real data is ever proposed. | With the provider decision |

# 24. Baseline Sign-Off

| Project | CivicConnect |
| --- | --- |
| Baseline Type | Milestone 2 – Architecture, Technology and Initial Design Baseline |
| Version | V2.0 |
| Date | 28/09/2026 |
| Scope reviewed | Yes - Milestone 1 Scope reviewed, no material changes identified |
| Requirements/traceability checked | Yes - RTM v2.0 |
| Risk review completed | Yes |
| Repository/governance controls checked | Yes |
| Outcome | Accepted |

## Sign-Off

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Rivan Maritz | Data & Security Lead | Rivan | 28/09/2026 |
| Nicholas Armin Vronka | Web App Lead | Nicholas | 28/09/2026 |
| Michiel Coenraad TerBlanche | Java App Lead | Mico | 28/09/2026 |

# 25. M3 Submission Information (PED v3.0)

Sections 1 to 24 are kept unchanged as the M1 and M2 project history. Sections 25 to 41 continue the same record for Milestone 3 and act as the evidence index: each claim points to the repository, CI run, test or register that supports it. Where M3 changes an earlier decision, the change is recorded in Section 28 rather than by editing the earlier section. Fields marked in yellow must be completed before submission.

| Item | Value |
| --- | --- |
| Team | Git Gud: Rivan Maritz, Nicholas Armin Vronka, Michiel Coenraad TerBlanche |
| GitHub repository | https://github.com/Nicholas005/SEN381-Project-CivicConnect |
| M3 release candidate | #27 Final-Frontendv2 |
| PED version | v3.0 |
| RTM location | Section 38 (RTM v3.0 Part C), continuing the RTM in Sections 5 and 12 |
| CI / test evidence |  |
| Staging / test environment | Neon for Database hosting and docker image for webpage environment staging. |
| Date submitted | 16/10/2026 |

# 26. M3 Overview and Current Build Status

## 26.1 Repository state at the start of M3 (16/10/2026)

The implementation currently sits on four branches. Only the database work is on main. The business logic, the tests and the frontend have not yet been merged, so there is no single integrated release candidate yet.

| Branch (head) | What it contains | On main? |
| --- | --- | --- |
| main (c5f36c2, PR #24) | Spring Boot 3.5.6 backend in controller / service / repository / model packages. PostgreSQL schema through Flyway (V1 schema, V2 category seed). Create, list, detail and history endpoints for requests. Docker Compose for local PostgreSQL with separate admin, owner, app and read-only roles. Dev-only permit-all security. | Yes |
| Java-Backend (fe992f1) | Spring Boot 4.1.1. Feature modules auth, request, assignment, status, audit, notification and reporting (ADR-M2-02). State pattern for five states (ED-007). StatusChangedEvent with a synchronous audit listener and an after-commit notification listener (ED-008). In-memory stores behind a RequestStore interface. 24 JUnit tests in three classes plus a context-load test. | No. Branched before PR #24, so it does not contain the database work. Also contains 676 committed node_modules files (D-01). |
| Frontend-V.2 (2487806) | React 18, TypeScript, Vite and Tailwind. Requester, staff and management pages, login and register. Development build runs against a mock API (VITE_USE_MOCK=true). | No |
| Frontend-Code (fe54a93) | Earlier frontend, superseded by Frontend-V.2. | No. Candidate for closing. |

## 26.2 Agreed M3 core scope

Final app needs to be completed and be fully functional before staging and hosting is implemented in the software’s lifecycle.

## 26.3 Path to the release candidate

- 1. Freeze scope (26.2) so no new features enter during integration.

- 2. Rebase Java-Backend onto main with node_modules removed. Keep the module packages (ADR-M2-02) and Spring Boot 4.1.x (ADR-M2-01-A1, CC-04).

- 3. Replace the in-memory stores with JPA adapters against the Flyway schema from PR #24, keeping the RequestStore interface (CC-03) and moving the in-memory store to test scope.

- 4. Replace DevSecurityConfig with real authentication and default-deny RBAC (ADR-M3-01, CC-06). This closes the release blocker D-05.

- 5. Connect Frontend-V.2 to the real API (VITE_USE_MOCK=false) and merge it.

- 6. Add the CI workflow (Section 30), make it a required check on main, then tag v3.0.0-rc1.

Every step goes through a feature branch and a Pull Request with two non-author approvals (Section 17).

# 27. M2 Baseline Conformance

| M2 decision | Implementation evidence | Conformance |
| --- | --- | --- |
| ADR-M2-01 and A1: Java 21, Spring Boot 4.1.x, Spring Data JPA, Spring Security, PostgreSQL 15+ | main pom.xml: Spring Boot 3.5.6. Java-Backend pom.xml: Spring Boot 4.1.1. | Partial. Two versions in the repository; resolved to 4.1.x at integration (CC-04). |
| ADR-M2-02: modular monolith | Java-Backend packages match the module table in 22.2. main uses package-by-layer. | Conforms on Java-Backend. main restructured on merge. |
| Section 6 and 20.3: data model | V1__init_schema.sql: users, categories (+ overdue_after_hours), user_category, service_requests (+ version), status_history, CHECK constraints, reference sequence. | Conforms with deviations CC-01, CC-02 and CC-05. |
| ED-007: State pattern | status package: SubmittedState, AssignedState, InProgressState, ResolvedState, ClosedState, StatusTransitionService. | Conforms for five states. No RejectedState although the schema allows REJECTED (D-03). |
| ED-008 and the ADR-M2-02 transaction rule | AuditLogService is a plain synchronous @EventListener. NotificationListener uses @TransactionalEventListener(AFTER_COMMIT). | Conforms. Rollback is only proven against the in-memory store until A-03 runs on PostgreSQL. |
| ASR-03: optimistic locking | service_requests.version column. RequestStore.replaceIfVersion and a two-thread test (T-08). | Conforms. |
| ASR-02: default-deny RBAC | main: DevSecurityConfig permits every request on the dev profile, and spring.profiles.active=dev is committed. Java-Backend: AccessControlService over an in-memory user directory, no login. | Does not conform yet. Release blocker (D-05). |
| Section 23.2: versioned migrations | flyway-core in main pom.xml, migrations V1 and V2. | Conforms. |
| Section 23.3: configuration and secrets | .env.example and application-example.properties committed. .env and application-dev.properties in .gitignore. Separate least-privilege database roles. | Conforms. |
| ADR-M2-02 enforcement: ArchUnit boundary test | Not present on any branch. | Not done (TD-04). |

# 28. Controlled Changes

Only significant deviations are recorded here. Each is proposed and needs two approvals before Section 24 is renewed. Minor coding choices are not listed.

| ID | Original decision | Evidence / problem | Revised decision | Consequence |
| --- | --- | --- | --- | --- |
| CC-01 | Section 20.3 shows CR-02, CR-03 and CR-04 as "Rejected", while Section 20.2 shows them as "Proposed". | The two tables were never reconciled. The V1 schema implements CR-02 and CR-03, and Java-Backend implements the CR-04 notification module. | Decide each CR formally. Recommended: approve CR-02 and CR-04 (FR-014 and FR-005 cannot be met without them); approve CR-03 and add RejectedState, or remove REJECTED from the schema. | RTM rows FR-005, FR-010 and FR-014 become "Changed". Section 24 sign-off renewed as 20.5 requires. |
| CC-02 | Section 6: ServiceRequest has createdAt. | V1 has no created_at column; submission time is the first status_history row (view v_request_overview). | Accept: one source of truth for submission time. | FR-013, FR-014 and FR-016 queries depend on a join to status_history (TD-03). |
| CC-03 | Section 6: persistence through Spring Data JPA repositories. | Business logic on Java-Backend was built against a RequestStore interface with an in-memory store, so it could be tested before the database existed. | Keep the interface. A JPA adapter implements it. The in-memory store moves to test scope. | Fast unit tests stay. One adapter layer added. Database behaviour still needs integration tests (A-01 to A-05). |
| CC-04 | ADR-M2-01-A1 proposed Spring Boot 4.1.x. | main is on 3.5.6, Java-Backend on 4.1.1. | Approve A1: 4.1.x for the release candidate. | main code ported to Spring Security 7 and Jackson 3 during the merge. R-014 closes once CI builds 4.1.x. |
| CC-05 | Section 6 did not fix the key type. | main uses UUID keys, Java-Backend uses Long. | Use UUID, because the schema is the controlled baseline. | Java-Backend DTOs, stores and tests change from Long to UUID. |
| CC-06 | Section 23.6 deferred the authentication mechanism. | jjwt 0.12.6 already added to main pom.xml; frontend has AuthContext and a login page. | Write ADR-M3-01 (signed JWT or database sessions) before auth is merged. Must keep the application stateless (ASR-05). | Decides token handling and CORS for the frontend. |

## 28.1 Engineering Decision Log additions

ADR-M2-02 listed "append ED-009 to the Engineering Decision Log" as a follow-up. The table in Section 11 stops at ED-007, so the later decisions are indexed here.

| ID | Decision | Record | Status |
| --- | --- | --- | --- |
| ED-008 | Observer pattern for notification and audit | Section 13 | Implemented (Java-Backend) |
| ED-009 | Modular monolith (ADR-M2-02) | Section 22 | Implemented (Java-Backend) |
| ED-010 | Deployment direction (ADR-M2-03) | Section 23.1 | Provider still open (Section 34) |
| ED-011 | Submission time from status_history (CC-02) | Section 28 | Proposed |
| ED-012 | Storage interface with JPA adapter (CC-03) | Section 28 | Proposed |
| ED-013 | UUID primary keys (CC-05) | Section 28 | Proposed |
| ADR-M3-01 | Authentication mechanism (CC-06) | Section 48 | Drafted at M4, awaiting approval |

# 29. Construction and Configuration Control

- Branching: one feature branch per area of work, merged into main through Pull Requests (#1, #17 to #24 in the main history).

- Review evidence: [OUTSTANDING: link two PRs that show reviewer comments, the author's response and re-approval, and confirm main's protection rule requires two approvals]. The Master Brief gives little credit for approval-only reviews.

- Configuration: Spring profiles separate local and hosted settings. Secrets come from environment variables or untracked files (.env, application-dev.properties). The database uses separate admin, owner, app and read-only roles, so the application does not connect as the schema owner.

- Findings: node_modules committed on Java-Backend (D-01); dev profile active by default (D-05); Section 17.2 states a Pull Request template exists, but there is no .github folder on any branch (D-06).

# 30. CI and Automated Verification

No CI workflow exists in the repository yet. The pipeline below is the design to implement in .github/workflows/ci.yml. GitHub Actions minutes, CodeQL, Dependabot and secret scanning are free for a public repository, which keeps NFR-007 intact.

| Check | Tool | Runs on | Gate rule |
| --- | --- | --- | --- |
| Build, unit and component tests | ./mvnw -B verify on JDK 21 | PR to main, push to main | Required status check. A failing build or test blocks the merge. |
| API / integration tests | Same job, postgres:15 service container, Flyway migrations | PR to main | Required. |
| Frontend build and type check | npm ci, npm run build (tsc --noEmit) | PR touching frontend/ | Required. |
| Static analysis | CodeQL (Java, TypeScript) | PR and weekly | High or critical alerts block the merge. |
| Dependency check | Dependabot alerts and dependency-review-action | PR | Blocks a PR that adds a dependency with a high-severity vulnerability. |
| Secrets | Secret scanning with push protection | Every push | Push refused. |
| Coverage | JaCoCo report uploaded as an artifact | PR | Report only, no percentage gate (Section 30.1). |

## 30.1 What a green pipeline does and does not show

A green run shows that the release candidate compiles, that the selected business rules hold for the chosen test data, that migrations apply to a clean PostgreSQL 15 database and that no known vulnerable dependency or committed secret was detected. It does not show that untested paths are correct, that the system performs under load, that it behaves the same on the hosted platform, or that the security configuration is complete. Coverage shows which lines ran during tests, not that their results were checked.

CI evidence links: [OUTSTANDING: first green run, one deliberately failing run that was blocked, and the run for the final release tag]

# 31. Quality Strategy Applied

Verification effort follows the ASR priority order in Section 21.2. The risks where a failure cannot be undone get the strongest checks.

| Risk / driver | Why it gets more verification | Verification applied |
| --- | --- | --- |
| ASR-01 audit and lifecycle (R-010, NFR-006) | A missing audit row or an illegal status jump cannot be repaired afterwards. | State-transition tests on valid and invalid paths, a fault-injection test that forces the audit write to fail, audit-order check, API test A-03. |
| ASR-02 confidentiality (R-003, R-008, NFR-003) | An exposed record is a privacy incident; RBAC is the team's least familiar area. | Negative tests per role and category scope, API tests for 401 and 403 (A-04), CodeQL, manual review of the security configuration. |
| ASR-03 integrity and concurrency (NFR-002) | Duplicate references or lost updates break the single trusted record. | 100,000-reference uniqueness test, two-thread conflict test, database UNIQUE constraint test (A-05). |
| Reporting (FR-013 to FR-016) | Wrong numbers mislead management but do not corrupt data. | Unit tests for counts, overdue and averages, with boundary data. |
| Usability (NFR-005) | Secondary driver; needs real participants. | Deferred to M4. Only the E2E journey covers the screens in M3. |

# 32. Black-Box, Integration and System Validation

## 32.1 Existing automated tests (Java-Backend branch)

These tests exist in the repository but have not yet been run in CI, so no execution evidence is claimed. The context-load test is not counted because it asserts nothing about behaviour.

| ID | Test | Level | Technique | Basis | Negative |
| --- | --- | --- | --- | --- | --- |
| T-01 | StatusTransitionServiceTest.cannotSkipStages | Component | State transition (invalid) | FR-010 | Yes |
| T-02 | …fullLifecycleIsAuditedInOrder | Component | State transition (valid path) | FR-010, NFR-006 |  |
| T-03 | …closedIsTerminal | Unit | State transition | FR-012, CR-05 | Yes |
| T-04 | …resolvingNeedsANote | Unit | Equivalence partitioning | FR-012 | Yes |
| T-05 | …onlyTheOwnerOrAManagerStartsWork | Unit | Decision table (role, ownership) | FR-009, FR-010 | Yes |
| T-06 | …staffOutsideTheirCategoryAreRefused | Unit | Negative | FR-006, ASR-02 | Yes |
| T-07 | …failedAuditWriteLeavesStatusUnchanged | Component | Fault injection | ASR-01, NFR-006 | Yes |
| T-08 | …simultaneousUpdatesGiveOneWinnerAndOneConflict | Component | Concurrency | ASR-03 | Yes |
| T-09 | …staffCannotAssignToSomeoneElseButManagersCan | Unit | Decision table | FR-009 | Yes |
| T-10 | …cannotAssignTwice | Unit | State transition | FR-009 | Yes |
| T-11 | …commentsAreRefusedAfterResolved | Unit | State transition | FR-011, CR-05 | Yes |
| T-12 | RequestServiceTest.submitStoresRequestWithReference | Unit | Equivalence partitioning (valid) | FR-001, NFR-002 |  |
| T-13 | …submissionIsValidated | Unit | Equivalence partitioning (invalid) | FR-001, FR-002 | Yes |
| T-14 | …onlyRequestersSubmit | Unit | Negative | FR-001, ASR-02 | Yes |
| T-15 | …referencesAreUnique (100,000 references) | Unit | Volume | NFR-002 |  |
| T-16 | …requesterSeesOnlyOwnRequests | Unit | Negative | FR-004, NFR-003 | Yes |
| T-17 | …staffQueueIsScopedToCategories | Unit | Equivalence partitioning | FR-006 | Yes |
| T-18 | …queueFiltersAndSortsByAge | Unit | Equivalence partitioning | FR-007 |  |
| T-19 | NotificationAndReportingTest.requesterIsToldAboutEachChange | Component | Event flow | FR-005 |  |
| T-20 | …notificationsCanBeMarkedReadOnlyByTheirOwner | Unit | Negative | FR-005, NFR-003 | Yes |
| T-21 | …statusCountsUseTheDefaultSevenDayRange | Unit | Boundary (range in or out) | FR-013 |  |
| T-22 | …overdueUsesTheThresholdAndIgnoresResolved | Unit | Boundary (73 h against 72 h) | FR-014 |  |
| T-23 | …averageResolutionTimeIsPerCategory | Unit | Calculation | FR-016 |  |
| T-24 | …reportingIsManagerOnly | Unit | Negative | FR-013, ASR-02 | Yes |

## 32.2 Gaps against the M3 minimum

| M3 minimum | Current position | Action |
| --- | --- | --- |
| 5 unit / component | 24 tests (T-01 to T-24) | Met once they run in CI. |
| 5 black-box functional | T-04, T-05, T-09, T-13, T-17, T-21, T-22 are designed from acceptance criteria at the service boundary. | Met. Strengthen T-13 and T-22 with exact boundaries (below). |
| 3 API / integration | None. | Write A-01 to A-05 (32.3). |
| 2 E2E / system | None. | Write E-01 and E-02 (32.4). |
| 3 negative | 16 tests. | Met. |
| 5 high-priority | All FR-001 to FR-012 tests are High priority. | Met. |
| 2 black-box techniques | State transition, decision table, equivalence partitioning, boundary value. | Met. |
| 1 performance scenario | None. | Run P-01 (Section 33). |

Boundary weaknesses: T-13 uses a 5-character description, which tests an invalid partition but not the FR-001 limit. Add 9 characters (rejected) and 10 characters (accepted), with leading and trailing spaces trimmed. T-22 checks 73 hours against a 72-hour threshold; add exactly 72 hours and 71 hours 59 minutes so the "older than" rule is pinned down.

## 32.3 Planned API / integration tests (PostgreSQL in CI)

| ID | Interaction verified | Input | Expected result | Basis |
| --- | --- | --- | --- | --- |
| A-01 | Controller, service, JPA and database for submission | POST /api/requests with an active category and a 25-character description | 201, Location header, reference matching CC- plus 8 digits, one status_history row with new_status SUBMITTED | FR-001, NFR-006 |
| A-02 | Validation at the API boundary | Unknown category; inactive category; 9-character description | 404, 404 and 400; no row written | FR-001, FR-002 |
| A-03 | State pattern and transaction on PostgreSQL | Status change Submitted to Resolved | 409; status unchanged; no new history row | FR-010, ASR-01 |
| A-04 | Security filter chain | Unauthenticated GET; requester reading another requester's request | 401; 403; no personal fields in the body | NFR-003, ASR-02 |
| A-05 | Database constraint as last line of defence | Insert two rows with the same reference_number | Second insert rejected by uq_service_requests_reference | NFR-002, ASR-03 |

## 32.4 Planned E2E / system tests (against staging)

- E-01 Request lifecycle: requester submits, staff assigns, starts work and resolves with a note, requester sees "Resolved" and the status message. Basis: FR-001, FR-003, FR-005, FR-009, FR-010, FR-012.

- E-02 Access scope: staff member for category A cannot see or open a category B request; manager sees both in the activity counts. Basis: FR-006, FR-013, NFR-003.

Tool: Playwright 1.64.1 (decided at M4). Specs are in frontend/e2e; results are recorded in Section 46.. Each executed test is recorded with the fields from M3 Section 11 (basis, reason, technique, input, expected, actual, status, evidence, trace, interpretation).

# 33. Performance and Load Test (P-01)

| Item | Plan |
| --- | --- |
| Operation | POST /api/requests (request submission). |
| Why it matters | It is the main requester action, and every submission writes two tables in one transaction (ASR-01), so it is the most expensive write path. |
| Target | NFR-001: 95th percentile at most 3 seconds with 50 concurrent users, measured on a warm instance (CR-01). |
| Tool | k6 (free). Script kept in the repository at tests/performance/submit.js. |
| Workload | One warm-up request. Ramp from 0 to 50 virtual users over 1 minute, hold 50 for 3 minutes, ramp down over 30 seconds. Each user submits a synthetic request, then waits 1 second. |
| Measures | Response time (median, 95th percentile, maximum), error rate and requests per second. Pass thresholds: p95 under 3000 ms and errors under 1%. |
| Environment | Docker Image |
| Result | Successful Launch with 3 second respond time from neon database |
| What it does not show | Municipal-scale load, cold-start delay (R-011), long-running stability, reporting queries under load, or behaviour once the database holds months of history. Each run also uses database compute hours on a free tier (R-012). |

# 34. Staging / Test Environment

Decision: [Decided at M4: simulated staging with Docker Compose, Section 50]. If the hosting spike in Section 23.6 has not been done, simulated staging is the lower-risk choice: the release-candidate image is built from the tag and run with Docker Compose next to a fresh PostgreSQL 15 container, using the hosted profile and a separate untracked .env.staging file.

| Aspect | Development | Staging |
| --- | --- | --- |
| Spring profile | dev (permit-all security) | hosted (RBAC enforced) |
| Frontend data | Mock API | Real API |
| Database | Local container with dummy seed data | Fresh database, migrations only, synthetic data generator (AS-08) |
| Build | Working copy | Image built from tag v3.0.0-rc1 |
| Secrets | Developer's .env | Platform secret store or .env.staging, never committed |

- Release identification: expose the build version and git commit on the health/info endpoint so the demo can show that the running build matches the submitted tag.

- Rollback: redeploy the previous tagged image. Flyway migrations only move forward, so take a pg_dump before deploying a build with a new migration; to roll back, restore the dump or apply a compensating migration. Staging holds synthetic data only, so losing it is acceptable.

- Differences that could still affect production: CPU and memory of the free tier, cold starts, network latency to an external database, hosting region (R-016) and real user data volumes.

# 35. Defects and Findings Register

| ID | Finding | Severity | Status | Fix / regression evidence |
| --- | --- | --- | --- | --- |
| D-01 | 676 node_modules files and a root package.json committed on Java-Backend. | Medium: review noise, unreviewed third-party code in history. | Fixed in final tree | Remove from the branch before merging; add node_modules/ to the root .gitignore. M4: node_modules and the root package.json are not in the merged project; node_modules/ is in .gitignore. The old Java-Backend branch still holds them in its history. |
| D-02 | On main, CreateRequestDto only checks that the description is not blank, so the FR-001 minimum of 10 characters is not enforced (Java-Backend does enforce it). | Medium: acceptance criterion not met. | Fixed | Keep the Java-Backend rule at integration. Regression: A-02 and the extended T-13. M4: description is trimmed and must be 10 to 2000 characters. Regression: BoundaryAndAcceptanceTest (9 and 10 characters, 2000 and 2001), RequestApiIT A-02. |
| D-03 | Schema allows REJECTED, but there is no RejectedState or transition. | Medium: FR-005 "rejected" feedback cannot happen. | Fixed | Resolve through CC-01. M4: RejectedState added (reason required, only from Submitted). Regression: StatusTransitionServiceTest rejection tests, LifecycleIT, E-04. CC-01 approval still pending. |
| D-04 | Two divergent backends (UUID or Long keys, Boot 3.5.6 or 4.1.1, layer or module packages). | High: no integrated release candidate. | Fixed in final tree | Section 26.3. M4: one backend (Spring Boot 4.1.1, UUID keys, module packages, JPA adapters on the Flyway schema) and one frontend. Final proof is the tagged commit and CI run (Section 42). |
| D-05 | spring.profiles.active=dev is committed in application.properties, and the dev profile permits every request with CSRF off. A deployment that does not override the profile exposes all data. | High: release blocker (ASR-02, NFR-003). | Open (reduced) | Remove the default profile; set it only through an environment variable; fail start-up if dev is active in a hosted environment. Regression: A-04. M4: DevSecurityConfig is gone; /api/** is authenticated by default, roles are enforced on the server and start-up fails without APP_AUTH_SECRET. Still open: the default profile is still dev (it loads the demo seed) and there is no start-up guard. Regression: A-04 tests. |
| D-06 | Section 17.2 says a PR template is in place, but no .github folder exists on any branch. | Low: governance evidence gap. | Fixed | Add .github/pull_request_template.md including the ADR-M2-02 boundary checklist line. M4: .github/pull_request_template.md added, including the ADR-M2-02 boundary checklist line. |
| D-07 | The context-load test on main needs a running database, so it fails without PostgreSQL. | Low | Fixed, pending CI | PostgreSQL service in CI (Section 30). M4: integration tests use a PostgreSQL service in .github/workflows/ci.yml; locally they skip when no database is reachable and fail when CI is set. Not yet proven by a CI run. |
| D-08 | Section 32.3 expects A-02 to return 404 for an unknown or inactive category. The API returns 400 (the category is part of the request body) and the tests assert 400. | Low: documentation deviation | Open (decision needed) | Change the PED line to 400, 400 and 400, or change the API. Evidence: docs/TEST_TRACEABILITY.md. |
| D-09 | The mock API returns 400 for an invalid status transition where the real backend returns 409. | Low | Open (accepted) | Only affects mock-mode demonstrations; the real-API system job is not affected. |
| D-10 | The health endpoint returns only status UP. It does not show the build version or git commit that Section 34 asks for. | Medium: release identification | Open | Expose version and commit on /api/health (build-info plugin) so the running build can be matched to the submitted tag. |
| D-11 | The original db/00_roles.sql committed real role passwords to the repository history. | High: credential exposure | Open | The delivered file uses CHANGE_ME placeholders. Rotate every role password and move them to the untracked .env. |
| D-12 | There is no rate limiting or lockout on POST /api/auth/login. | Medium: ASR-02, credential guessing | Open | Add a limiter or platform protection before real users are onboarded. |
| D-13 | Managers can view reports but the web interface has no screen for them to act on a request (the API allows it). | Low: usability limitation | Open (accepted) | Recorded as a limitation in Section 52. |

# 36. Technical Debt Register

| ID | Debt | Consequence if left | Planned action | Owner |
| --- | --- | --- | --- | --- |
| TD-01 | In-memory stores and user directory used as main code on Java-Backend. | Behaviour on PostgreSQL (locking, rollback) is unproven. | JPA adapters (CC-03); in-memory store to test scope. | Michiel. Repaid in code: JPA adapters (Jpa*Store) are the main code and the in-memory stores are in test scope. PostgreSQL proof (RollbackIT, ConcurrencyIT) is written but not yet run in CI. |
| TD-02 | overdue_after_hours defaults to 72 for every category; the schema marks it as a placeholder. | Overdue reports reflect a guess, not the sponsor's service levels. | Confirm thresholds per category with the sponsor. | Rivan. Retained: 72 hours is still a placeholder. Confirm per-category thresholds with the sponsor. |
| TD-03 | Submission time is derived from status_history (CC-02). | Reporting queries slow down as history grows. | Index review; measure in P-01 follow-up. | Rivan. Retained and accepted: no index review or P-01 follow-up was done. |
| TD-04 | ArchUnit boundary test promised in ADR-M2-02 not written. | Module boundaries rely on reviewers noticing violations (R-010). | Add the test to the CI suite. | Michiel. Repaid in code: ArchitectureTest (4 rules) is in the CI suite. It has not been executed yet. |
| TD-05 | No tested backup and restore (Section 23.6). | Data loss on the free database cannot be recovered with confidence. | One recorded pg_dump restore before the M3 demo. | Rivan. Retained: no backup and restore has been recorded. |
| TD-06 | Frontend has no automated tests and has only run against the mock API. | API contract mismatches appear late. | E-01 and E-02; contract check at integration. | Nicholas. Repaid in part: 37 Vitest tests and 5 Playwright tests (mock API). The real-API run is the system job in CI, not yet run. |

# 37. Risk Register Update (M3 review)

| Risk | Change | Reason | Owner |
| --- | --- | --- | --- |
| R-017 (new) | Integrating the divergent branches late in M3 delays the release candidate. Priority High. | D-04; the database work and the business logic were built apart and use different key types and versions. | Michiel (proposed) |
| R-018 (new) | Development security settings reach a hosted environment. Priority High. | D-05. | Rivan (proposed) |
| R-019 (new) | Tests exist but never run, giving false confidence. Priority Medium. | No CI yet; tests could not be executed during this review. | Nicholas (proposed) |
| R-004 | Partly materialised; now an issue. | The learning curve split the work across branches. | Entire team |
| R-006 | Watch. | Large single commits ("Backend", "Frontend code added to the project") weaken the progressive-history evidence. | Nicholas |
| R-008 | Still open; highest security risk. | No RBAC implemented yet. | Rivan |
| R-010 | Reduced. | State pattern implemented with T-01 to T-03; ArchUnit test outstanding (TD-04). | Rivan |
| R-014 | Reduce to Low once CI builds Spring Boot 4.1.x. | Java-Backend already uses 4.1.1. | Michiel |

# 38. RTM v3.0 Part C: Implementation and Verification

Same requirement IDs and order as Parts A and B (Section 12). Execution evidence is "Pending CI" until a run exists; it must not be filled in from local runs without a retained report.

M4 note: this table is preserved as the M3 record. The final status of every requirement is in Section 49 (RTM Part D).

| ID | Acceptance criterion (short) | Implementation | Test case(s) | Defect / status |
| --- | --- | --- | --- | --- |
| FR-001 | Category and description of 10+ characters saves and shows a unique reference within 3 s | RequestService.create; POST /api/requests | T-12, T-13, A-01, A-02, E-01 | D-02; In development |
| FR-002 | No category blocks submission | CategoryCatalog; categories.active; foreign key | T-13, A-02 | In development |
| FR-003 | Own request shows stage and last update | GET /api/requests/{id} | E-01 | Gap: no unit test |
| FR-004 | History lists every own request | RequestService.listForRequester | T-16 | In development |
| FR-005 | Status-specific message after each change | NotificationListener (after commit) | T-19, T-20, E-01 | CC-01 (CR-04) |
| FR-006 | Staff see only authorised categories | AccessControlService; user_category | T-06, T-17, A-04, E-02 | D-05 blocker |
| FR-007 | Category filter, oldest first | RequestFilter, RequestSort | T-18 | In development |
| FR-008 | Full detail incl. history and comments | RequestDetailDto | None yet | Gap |
| FR-009 | Owner and assignment time recorded | AssignmentService | T-05, T-09, T-10 | In development |
| FR-010 | Invalid jump rejected; valid steps timestamped | State classes; StatusTransitionService | T-01, T-02, A-03, E-01 | In development |
| FR-011 | Comment stored with author and time | RequestComment | T-11 (refusal only) | Gap: positive case |
| FR-012 | Resolve with note, then read-only | ResolvedState, ClosedState | T-03, T-04, T-11 | In development |
| FR-013 | Counts by status, default 7 days | ReportingService | T-21, T-24 | In development |
| FR-014 | Overdue by category threshold | ReportingService; overdue_after_hours | T-22 | CC-01 (CR-02); TD-02 |
| FR-015 | Category filter on activity view | ReportingService (category parameter) | None yet | Gap |
| FR-016 | Average resolution time per category | ReportingService | T-23 | In development |
| NFR-001 | p95 at most 3 s, 50 users, warm | Submission path | P-01 | Not run |
| NFR-002 | Zero duplicates in 100,000 | Database sequence and UNIQUE constraint | T-15, A-05 | In development |
| NFR-003 | No personal data without authorisation | Spring Security (pending ADR-M3-01) | T-14, T-16, T-24, A-04 | D-05 blocker |
| NFR-004, 005, 007 | Uptime, usability, cost | Hosted environment | M4 | Deferred |
| NFR-006 | Gap-free ordered audit history | AuditLogService; status_history | T-02, T-07, A-01 | In development |

Every row's expected result is the acceptance criterion in Section 3. The execution-evidence column ([OUTSTANDING: CI run link per row]) is filled from the release-candidate run only.

# 39. Release Evidence Summary and Residual Risk

Provisional, as at 16/10/2026. Re-run this table against the tagged release candidate before submission.

M4 note: this table is the M3 record. The re-run against the final build is in Sections 46 and 50.

| Evidence area | Result now | Interpretation | Action |
| --- | --- | --- | --- |
| Build and CI | No pipeline | Nothing is verified automatically. | Section 30. |
| Automated regression | 24 tests written, not executed | Core rules are specified as tests, but not proven. | Run in CI. |
| API / integration | None | Database behaviour unproven. | A-01 to A-05. |
| System / E2E | None | No integrated journey exists yet. | E-01, E-02. |
| Static / security | Not run; D-05 found by review | Release-blocking configuration risk. | CodeQL, fix D-05. |
| Performance | Not run | NFR-001 unproven. | P-01. |
| Known defects | D-01 to D-07 open; D-04 and D-05 High | Two release blockers. | Close before tagging. |
| Acceptance | Partial | Gaps on FR-003, FR-008, FR-011, FR-015. | Add tests or record as limitations. |

Classification now: NOT READY. There is no integrated build, no CI, RBAC is missing and D-05 is open. Target at submission: CONDITIONALLY READY, if Section 26.3 is complete, D-04 and D-05 are closed and the only remaining items are the limitations below. [Recorded at M4: see the final classification in Section 50]

| Residual risk | Why it remains | Current mitigation | Next action / owner |
| --- | --- | --- | --- |
| Production-scale load untested | A student environment cannot represent a municipality. | P-01 at 50 users; single-instance design reviewed. | Re-test on representative infrastructure before real use. |
| Free-tier cold start and quotas (R-011, R-012) | Provider limits outside the team's control. | Warm-instance rule; local Docker fallback. | Monitor during M4 hosting. |
| Security review not independent | All reviewers are team members. | CodeQL, negative tests, two-person review. | Request a lecturer or peer review before M4. |
| Time handling | Overdue and reporting depend on UTC storage and SAST display. | timestamptz columns; fixed test clock. | Add a test across midnight SAST. |

# 40. AI Usage Register: M3 Additions

Continues the register in Section 18.

| Date | Student | Tool | Engineering task | AI contribution | Verification | Decision | Issues found |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 16/10/2026 | Nicholas Armin Vronka | Claude AI | Gap analysis of PED v2.0 and the repository against the M3 brief; draft of PED v3.0 Sections 25 to 41 | Draft sections, findings D-01 to D-07, mapping of existing tests to requirements | Had the whole team review the finalised document and edit it so that it is closer to our vision of the project | Draft kept for team review | The AI could not build or run the tests (no Maven access), so all execution results were left pending. |

# 41. Outstanding M3 Actions

| Action | Section | Owner | Done |
| --- | --- | --- | --- |
| Write ADR-M3-01 (authentication) | 28 | Rivan Maritz | ☐ |
| Integrate branches and remove node_modules (D-01, D-04) | 26.3 | Nicholas Armin Vronka | ☐ |
| Fix D-05 and implement RBAC | 35 | Michiel Coenraad TerBlanche | ☐ |
| Add ci.yml, CodeQL, Dependabot, secret scanning; make CI a required check | 30 | Michiel Coenraad TerBlanche | ☐ |
| Add PR template (D-06) | 35 | Michiel Coenraad TerBlanche | ☐ |
| Write A-01 to A-05, E-01, E-02; extend T-13 and T-22 | 32 | Nicholas Armin Vronka | ☐ |
| Run P-01 and record results | 33 | Rivan Maritz | ☐ |
| Set up staging and record the rollback test | 34 | Rivan Maritz | ☐ |
| Tag v3.0.0-rc1; fill Sections 25, 38 and 39 from that run | 25, 38, 39 | Nicholas Armin Vronka | ☐ |
| Export PED v3.0 to PDF | - | Michiel Coenraad TerBlanche | ☐ |

# 42. M4 Submission Information (PED v4.0 Final)

PED v3.0 is continued as PED v4.0. Sections 1 to 41 keep the project history; where M4 changed a status, the cell was updated and marked "M4". Sections 42 to 53 are the closing record. This is not a new report. Fields highlighted in yellow need evidence that only the team can supply.

| Item | Value |
| --- | --- |
| Team name / number | Git Gud |
| Team members | Rivan Maritz, Nicholas Armin Vronka, Michiel Coenraad TerBlanche |
| GitHub repository URL | https://github.com/Nicholas005/SEN381-Project-CivicConnect |
| Final commit / tag / release | Merge pull request #45 from Nicholas005/Hosting-PED-Control |
| PED version | v4.0 Final |
| Final RTM location | Section 49 (RTM Part D), continuing RTM Parts A and B (Sections 5 and 12) and Part C (Section 38) |
| Registers | Risk: Sections 37 and 47. Defect: Section 35. Technical debt: Section 36. Decision/ADR/Change: Sections 28 and 48. AI usage: Sections 18 and 40 |
| CI / test evidence | https://github.com/Nicholas005/SEN381-Project-CivicConnect/actions/runs/39121194829 Workflow: .github/workflows/ci.yml. Test map: docs/TEST_TRACEABILITY.md |
| Final product access / demonstration | Local build of the tagged commit with Docker Compose (Section 50). Demo accounts are in the dev seed (db/dev). http://localhost:5173/login |
| Date submitted | 18/10/2026 |

# 43. Final Release Baseline and What Changed Since M3

The product assessed is the integrated CivicConnect application: one Spring Boot 4.1.1 backend (Java 21) with a React 18 / TypeScript frontend, served from one jar, on a PostgreSQL schema managed by Flyway V1 to V3. The evidence in this document refers to that build only. Merge pull request #45 from Nicholas005/Hosting-PED-Control

## 43.1 Changes between the M3 release candidate plan and the final build

| M3 position (Section 26.1) | Final position | Reference |
| --- | --- | --- |
| Four branches; no integrated build. | One project: backend, frontend, database scripts and Docker files together. The unused earlier frontend branch is not part of it. | D-04 |
| In-memory stores and user directory were main code. | Spring Data JPA adapters (Jpa*Store, JpaUserDirectory) implement the same interfaces; in-memory stores moved to test scope. | CC-03, TD-01 |
| No real authentication; permit-all on the dev profile. | Login with BCrypt passwords and signed HS256 tokens, stateless; /api/** authenticated by default; roles enforced on the server; start-up fails without a 32-character secret. | CC-06, ADR-M3-01 (Section 48), D-05 |
| No RejectedState. | RejectedState added: a reason is required and only a Submitted request can be rejected. | D-03, CC-01 |
| No comments table or comments in the schema view. | V3 migration adds request_comments (append-only) and updates the overview view; comments are visible to staff and never to requesters. | FR-011 |
| Frontend ran on a mock API only. | Frontend calls the real API (VITE_USE_MOCK=false). Mock data matches the database seed. | TD-06 |
| 24 unit tests, none run; no API, E2E or performance tests; no CI. | 60 unit tests, 33 integration tests (PostgreSQL), 5 browser tests, 37 frontend unit tests, k6 script, GitHub Actions workflows. Execution status is in Section 46. | Sections 30 to 33 |
| No PR template; no .github folder. | .github holds the workflows, Dependabot configuration and the PR template. | D-06 |

## 43.2 What M4 deliberately did not add

No new feature, architecture, security capability, performance programme or monitoring was introduced for M4. The only application change made while finalising was the Location header on POST /api/requests, which A-01 expects.

# 44. M1 Scope to Final Delivery

Every in-scope commitment from Section 2 is listed with its final status. Status categories: IMPLEMENTED, PARTIALLY IMPLEMENTED, NOT IMPLEMENTED, CHANGED/REMOVED THROUGH APPROVED CHANGE. Out-of-scope and future items are shown separately so they are not read as failed commitments.

## 44.1 In-scope commitments (Section 2.1)

| M1 scope item | M1 priority / status | Final status | Acceptance criteria | Evidence | Conclusion / reason |
| --- | --- | --- | --- | --- | --- |
| Requester submits a request with category, description and details (FR-001) | High / In scope | IMPLEMENTED | Met | T-12, T-13, A-01, A-02, E-01, E-05 | Delivered as committed. The 3-second response is only checked indirectly (P-01 not run). |
| Controlled category list (FR-002) | High / In scope | IMPLEMENTED | Met | T-13, A-02, categories table and foreign key, E-05 | Delivered as committed. |
| Requester views status of a request (FR-003) | High / In scope | IMPLEMENTED | Met | BoundaryAndAcceptanceTest, LifecycleIT, E-01 | Closes the M3 gap "no unit test". |
| Requester views history of requests (FR-004) | High / In scope | IMPLEMENTED | Met | T-16, RequestApiIT | Delivered as committed. |
| Requester receives feedback on accept, reject, update, complete (FR-005) | High / In scope | IMPLEMENTED | Met | T-19, T-20, LifecycleIT, E-01, E-04 | In-app notifications only (no email or SMS), which the criterion allows. Rejection exists through CR-03. |
| Staff see only requests they are authorised for (FR-006) | High / In scope | IMPLEMENTED | Met | T-06, T-17, A-04, E-02 | Delivered. Enforced on the server, not only in the interface. |
| Staff search, filter and sort (FR-007) | High / In scope | IMPLEMENTED | Met | T-18, LifecycleIT | Delivered as committed. |
| Staff view full request detail (FR-008) | High / In scope | IMPLEMENTED | Met | BoundaryAndAcceptanceTest, RequestAssemblerTest | Closes the M3 gap. |
| Staff assign or accept responsibility (FR-009) | High / In scope | IMPLEMENTED | Met | T-05, T-09, T-10, E-01 | Delivered. Managers can assign through the API but the interface has no manager action screen (D-13). |
| Staff update status through controlled transitions (FR-010) | High / In scope | IMPLEMENTED | Met | T-01, T-02, A-03, E-01 | Delivered with the State pattern (ED-007). |
| Staff record comments and resolution notes (FR-011) | High / In scope | IMPLEMENTED | Met | T-11, BoundaryAndAcceptanceTest, DatabaseConstraintIT | Positive case added since M3. |
| Staff resolve or close requests (FR-012) | High / In scope | IMPLEMENTED | Met | T-03, T-04, T-11, E-01 | Delivered. Resolved and closed are read-only. |
| Management views service activity: open, overdue, resolved, closed (FR-013, FR-014) | High / In scope | IMPLEMENTED | Met | T-21, T-22, T-24, LifecycleIT | Overdue thresholds are placeholders at 72 hours (TD-02). The mechanism is complete. |
| Management views requests by category or status (FR-015) | Medium / In scope | IMPLEMENTED | Met | BoundaryAndAcceptanceTest, dashboard category filter | Closes the M3 gap. |
| Management supports accountability and analysis (FR-016) | Medium / In scope | IMPLEMENTED | Met | T-23 | Average time to resolution per category. |

## 44.2 Non-functional commitments (Section 3.2)

| Item | M1 priority | Final status | Acceptance criteria | Evidence | Conclusion / reason |
| --- | --- | --- | --- | --- | --- |
| NFR-001 submission within 3 s at 50 users | Medium | NOT IMPLEMENTED (not verified) | Not met | P-01 script exists; never run | The feature exists but the criterion needs the load test. It scores zero until P-01 is run. |
| NFR-002 unique reference | High | IMPLEMENTED | Met | T-15 (100,000), A-05, database sequence and UNIQUE constraint | Delivered. The constraint was also confirmed on a real PostgreSQL. |
| NFR-003 data protected from unauthorised access | High | PARTIALLY IMPLEMENTED | Partially met | A-04, T-06, T-14, T-16, T-24, E-03; CodeQL not run | Controls and tests exist. The criterion asks for an independent review or scan, which has not happened. No rate limiting on login (D-12). |
| NFR-004 99% uptime in business hours | Medium | NOT IMPLEMENTED | Not met | None | Needs 30 days of hosting and a monitor. The team stayed in staging (Section 50). Carried to future work, not a failed build. |
| NFR-005 usability: 80% unaided in 5 minutes | Medium | NOT IMPLEMENTED | Not met | None | Needs moderated participants; none were recruited. |
| NFR-006 every status change audited | High | IMPLEMENTED | Met | T-02, T-07, A-01, A-03, RollbackIT, append-only trigger | Delivered. Audit write is in the same transaction as the status change. |
| NFR-007 cost within free tiers | High | PARTIALLY IMPLEMENTED | Partially met | Free tooling only; no billing dashboard | No paid service is used, but nothing is hosted, so the criterion cannot be shown over time. |

## 44.3 Out of scope and future items (Sections 2.2 and 2.3)

| Item | M1 status | Final status | Evidence | Conclusion |
| --- | --- | --- | --- | --- |
| Payment processing or billing | Out of scope | Still out of scope | PED Section 2.2 | Correctly excluded. |
| Automated, rules-based or AI request routing | Out of scope | Still out of scope | Assignment is manual (AssignmentService) | Correctly excluded. |
| Integration with emergency or dispatch systems | Out of scope | Still out of scope | PED Section 2.2 | Correctly excluded. |
| Native mobile apps | Out of scope | Still out of scope | Responsive web interface | Correctly excluded. |
| Automated or optimised assignment | Future | Still deferred | PED Section 2.3 | Not a failed commitment. |
| Requester satisfaction survey | Future | Still deferred | PED Section 2.3 | Not a failed commitment. |
| Public analytics dashboard | Future | Still deferred | PED Section 2.3 | Not a failed commitment. |

## 44.4 Approved scope changes

Changes CC-01 to CC-06 and CR-02 to CR-04 did not remove or add any M1 acceptance criterion, so the denominator in Section 45 is unchanged. CR-02 (per-category overdue threshold) and CR-04 (notifications) are what FR-014 and FR-005 need. CR-03 (rejected state) added behaviour but no new criterion.

Conclusion: the delivered functional scope is complete and coherent. All 16 functional requirements are implemented. What remains incomplete is the non-functional evidence that needs a hosted environment, load, an independent review or real participants.

# 45. Scope Completion Percentage

Method (Final Project brief): Met = 1.0, Partially Met = 0.5, Not Met = 0.0. Scope Completion % = sum of values divided by 23 applicable acceptance criteria (16 FR and 7 NFR), times 100. The statuses below are the team's draft based on the evidence in Section 46 and must be confirmed once the CI run exists.

| Group | Criteria | Met (1.0) | Partially met (0.5) | Not met (0.0) | Points |
| --- | --- | --- | --- | --- | --- |
| Functional FR-001 to FR-016 | 16 | 16 | 0 | 0 | 16.0 |
| NFR-002, NFR-006 | 2 | 2 | 0 | 0 | 2.0 |
| NFR-003, NFR-007 | 2 | 0 | 2 | 0 | 1.0 |
| NFR-001, NFR-004, NFR-005 | 3 | 0 | 0 | 3 | 0.0 |
| Total | 23 | 18 | 2 | 3 | 19.0 |

Scope Completion Percentage = 19.0 / 23 = 82.6%. This is in the 80 to 89% band: substantial completion, provided the critical evidence is credible.

## 45.1 How far the result can be trusted

-  The 16 functional criteria are scored Met on evidence from the build environment, not from CI. The 80% line is 18.4 points. If one functional criterion drops to Partially Met in CI the total is 18.5 (80.4%); if two drop it is 18.0 (78.3%) and the band changes. The team should re-score after the CI run.

-  NFR-001 is the cheapest improvement: running P-01 and passing it adds 1.0 (20.0 / 23 = 87.0%). A failing result would be recorded as Not Met, as now.

-  High-priority criteria that are not fully met: NFR-003 (no independent review or scan, no login rate limiting) and NFR-007 (not hosted, so not measurable). Both are justified by the staging decision in Section 50 and are not hidden.

-  Medium-priority omissions: NFR-001 (not run), NFR-004 and NFR-005 (need hosting and participants). No Must-have functional requirement is omitted.

-  The percentage is a control, not the judgement. It does not make the product ready for production; Section 50 says it is not.

# 46. Final Acceptance and Verification Evidence

M4 adds no testing quota. This section records what exists, where it was run, and what is still unproven. "Build environment" means a run outside GitHub Actions; it is useful evidence but is not the CI evidence the PED requires.

## 46.1 Execution status of the verification evidence

| Evidence | Written | Executed | Result | Where / limit |
| --- | --- | --- | --- | --- |
| Unit and component tests (T-01 to T-24 and additions) | 60 | 56 | All 56 passed | Build environment, with a stand-in JUnit runner and in-memory test doubles. Not run through Maven. |
| ArchUnit rules (ADR-M2-02) | 4 | 0 | Not run | Written to run in ./mvnw verify. |
| API / integration tests on PostgreSQL (A-01 to A-05 and more) | 33 | 0 | Not run | The SQL they depend on (unique reference, append-only triggers, CHECK constraints, application role permission errors) was checked by hand on PostgreSQL. The Spring application itself was run by the team. |
| Frontend unit tests (Vitest) | 37 | 37 | All passed | Build environment. |
| Browser tests E-01 to E-05 (Playwright) | 5 | 5 | Passed, repeated 30 times | Mock API only. Real-API run is the CI system job. |
| Performance P-01 (k6) | 1 | 0 | Not run | Script is tests/performance/submit.js. |
| CodeQL, dependency review, secret scanning | Configured | 0 | Not run | Workflows exist; GitHub settings must be switched on. |
| Whole product demonstration | - | Yes | The team ran the merged project and reported it working | Local. Repeat on the tagged build. |

## 46.2 Critical journeys and acceptance criteria re-checked

| Critical requirement / journey | Acceptance criterion | Final status | Evidence | Strength |
| --- | --- | --- | --- | --- |
| FR-001 submit a request | 10+ character description, unique reference shown within 3 s | Met | T-12, T-13, boundary tests (9 and 10 characters), A-01, E-01, E-05 | Strong; the 3 s part is unmeasured |
| FR-010 controlled transitions | Submitted to Resolved directly is rejected; valid steps timestamped | Met | T-01, T-02, A-03, E-01 | Strong |
| FR-006 / NFR-003 access scope | Staff see only authorised categories; no data for the wrong role | Met / Partially met | T-06, T-17, A-04, E-02, E-03 | Strong on tests; no independent review |
| NFR-006 / ASR-01 audit | Gap-free ordered history; failed audit write leaves status unchanged | Met | T-02, T-07, RollbackIT, append-only trigger | Strong |
| NFR-002 / ASR-03 integrity | No duplicate references; one winner on concurrent update | Met | T-15, T-08, A-05, ConcurrencyIT | Strong |
| FR-013 / FR-014 reporting | Counts by status over 7 days; overdue by category threshold | Met | T-21, T-22 and boundary tests | Medium; thresholds are placeholders |
| NFR-001 performance | p95 at most 3 s at 50 users | Not met | None | Weakest evidence |

Strongest evidence: FR-010, NFR-006, NFR-002 (several independent techniques, including a database-level check). Weakest: NFR-001, NFR-004, NFR-005 (no execution). A working screen alone does not prove a requirement: FR-006 passes the interface test E-02 but is only accepted because A-04 shows the server refuses the same request without the interface.

Regression: no previously passing acceptance criterion was found to fail after the final fixes. The one behaviour change in the final build (Location header on creation) is covered by A-01.

# 47. M3 Issue Closure

Defects D-01 to D-13 and technical debt TD-01 to TD-06 were updated in place in Sections 35 and 36. This section summarises the position and closes the remaining M3 items.

## 47.1 Summary

| M3 item | Final conclusion | Evidence |
| --- | --- | --- |
| Open defects D-01 to D-07 | D-01, D-02, D-03, D-04, D-06 fixed in the final tree. D-07 fixed, pending CI. D-05 reduced but open: permit-all removed, but the default profile is still dev. | Section 35 |
| New findings at M4 (D-08 to D-13) | D-11 (committed passwords) is High and open. D-10 and D-12 are Medium and open. D-08, D-09, D-13 are Low. | Section 35 |
| Failed or conditional quality checks | M3 had no API, E2E, performance or CI evidence. API and E2E tests now exist (E2E run on mock only); performance and CI remain unrun and are carried as known limitations. | Section 46 |
| Residual risks (Section 39) | Production-scale load: untested. Free-tier limits: not hit because nothing is hosted. Security review: still by team members only. Midnight SAST time handling: no test written. | Section 39 |
| Technical debt | Repaid in code: TD-01, TD-04, TD-06 (in part). Retained with consequence: TD-02, TD-03, TD-05. | Section 36 |
| Incomplete integration | Finalised: one backend, one frontend, one database. Mock API still exists for demonstrations and differs in one status code (D-09). | Section 43 |
| Release / staging evidence | Staging plan reused. No hosted environment exists; simulated staging with Docker Compose is the declared state. | Sections 34, 50 |

## 47.2 Risk register: final status

| Risk | M3 position | Final status | Consequence |
| --- | --- | --- | --- |
| R-017 late integration of branches | High | Closed: branches integrated | It did delay the work and cost the team its early test time. |
| R-018 dev settings reach a hosted environment | High | Open (reduced) | Default profile is dev, so an unconfigured deployment loads demo accounts. Reason for the no-go decision. |
| R-019 tests exist but never run | Medium | Open | Still true for the integration tests until a CI run exists. |
| R-004 learning curve split the work | Materialised | Closed as an issue; lesson recorded | See Section 51. |
| R-006 large single commits | Watch | Open | Authentic history must be preserved; do not squash it before submission. |
| R-008 no RBAC | Highest security risk | Reduced | RBAC implemented and tested; independent review still missing. |
| R-010 audit and boundary drift | Reduced | Reduced | ArchUnit rules written; not yet run. |
| R-014 Spring Boot 4.1.x | Reduce once CI builds | Open until CI runs | The project builds on 4.1.1 locally. |

# 48. Decisions and Controlled Changes: Final Status

## 48.1 Controlled changes

| ID | Final status | Evidence in the final build | Still needed |
| --- | --- | --- | --- |
| CC-02 submission time from status_history | Implemented | v_request_overview | Approval. Index review (TD-03). |
| CC-03 storage interfaces with JPA adapters | Implemented | RequestStore and other ports with Jpa* adapters; in-memory in test scope | Approval. |
| CC-04 Spring Boot 4.1.x | Implemented | pom.xml on 4.1.1 | Approval; CI build. |
| CC-05 UUID keys | Implemented | All entities and DTOs | Approval. |
| CC-06 authentication | Implemented | ADR-M3-01 draft below | Approval |

## 48.2 ADR-M3-01: Authentication mechanism (draft for approval)

| Field | Content |
| --- | --- |
| Context | The application must be stateless (ASR-05) and default-deny (ASR-02). The frontend is a single-page app served by the same jar. |
| Decision | Signed JSON Web Tokens (HS256) sent in the Authorization header. Passwords are stored as BCrypt hashes. Token lifetime defaults to 480 minutes. The signing secret comes from APP_AUTH_SECRET and the application will not start if it is shorter than 32 characters. CORS allows only the configured origins. Registration always creates a requester. All /api/** endpoints require a valid token except /api/auth/** and /api/health. |
| Alternatives | Database-backed sessions: rejected because they add server state. A third-party identity provider: rejected for cost and scope. |
| Consequences | Good: no session store, simple to test (JwtServiceTest, AuthServiceTest, AuthApiIT). Cost: a token cannot be revoked before it expires; there is no refresh flow; there is no login rate limiting (D-12); a hand-rolled token implementation needs an independent review. |
| Status | Michiel Coenraad TerBlanche Rivan Maritz 18/10/2026 |

## 48.3 Decisions with the clearest consequences

| Decision | Positive consequence | Negative consequence |
| --- | --- | --- |
| ADR-M2-02 modular monolith with storage interfaces (CC-03) | The business logic built on in-memory stores moved to PostgreSQL by adding adapters; the tests kept running. | The backend and the database were built apart (D-04) and the merge was the largest piece of late work. |
| Database-first with Flyway and separate roles (ED-010 area, Section 23.3) | The database enforces what the application should: unique references, append-only history, CHECK constraints, and the application role cannot alter them. | Role passwords were committed (D-11); a second set of conventions (UUID, layers) had to be reconciled. |
| State pattern and Observer events (ED-007, ED-008) | Illegal transitions are impossible by construction; audit is in the same transaction as the change; notification is after commit. | More classes to test; a failure in the after-commit listener must never undo the status change. |

# 49. Final RTM Part D: Final Implementation, Evidence and Status

This continues the RTM (Parts A, B and C); it is not a new matrix. Trace: stakeholder need, requirement, acceptance criterion (Section 3), design, final implementation, final evidence, defect or status, outcome. Execution evidence refers to Section 46: "BE" is the build environment, "CI" is GitHub Actions (not yet run).

| ID | Stakeholder need | Final implementation | Final evidence | Defect / issue | Final status |
| --- | --- | --- | --- | --- | --- |
| FR-001 | Requester: fast, simple submission | RequestService.create; POST /api/requests (201 and Location) | T-12, T-13, A-01, A-02, E-01, E-05 (BE: unit, E2E; CI: A-01, A-02) | D-02 fixed; D-08 | Met |
| FR-002 | Requester: controlled categories | CategoryCatalog; categories table; foreign key | T-13, A-02, E-05 | None | Met |
| FR-003 | Requester: visibility of status | GET /api/requests/{id}; RequestAssembler | BoundaryAndAcceptanceTest, E-01 | M3 gap closed | Met |
| FR-004 | Requester: history | RequestService.listForRequester | T-16, RequestApiIT | None | Met |
| FR-005 | Requester: feedback | NotificationListener (after commit); NotificationQueryService | T-19, T-20, LifecycleIT, E-01, E-04 | CC-01 approval pending | Met |
| FR-006 | Staff: relevant queue only | AccessControlService; user_category; JWT filter | T-06, T-17, A-04, E-02 | D-05 reduced | Met |
| FR-007 | Staff: filter and sort | RequestFilter, RequestSort | T-18, LifecycleIT | None | Met |
| FR-008 | Staff / supervisor: full detail | RequestAssembler detail view | BoundaryAndAcceptanceTest, RequestAssemblerTest | M3 gap closed | Met |
| FR-009 | Supervisor: assignment | AssignmentService | T-05, T-09, T-10, E-01 | D-13 (no manager screen) | Met |
| FR-010 | Staff: controlled status | State classes; StatusTransitionService | T-01, T-02, A-03, E-01 | D-09 (mock 400 vs 409) | Met |
| FR-011 | Staff: record actions | RequestComment; request_comments | T-11, BoundaryAndAcceptanceTest, DatabaseConstraintIT | M3 gap closed | Met |
| FR-012 | Staff: resolve and close | ResolvedState, ClosedState | T-03, T-04, T-11, E-01 | None | Met |
| FR-013 | Management: activity | ReportingService.countsByStatus | T-21, T-24, LifecycleIT | None | Met |
| FR-014 | Management: overdue | ReportingService.overdue; overdue_after_hours | T-22 and boundary tests | TD-02 placeholder thresholds | Met |
| FR-015 | Management: by category | Category parameter on reporting; dashboard filter | BoundaryAndAcceptanceTest | M3 gap closed | Met |
| FR-016 | Management: accountability | ReportingService.summary | T-23 | None | Met |
| NFR-001 | Requester / sponsor: acceptable speed | Submission path | P-01 (not run) | Not run | Not met |
| NFR-002 | Sponsor: one trusted record | Sequence; UNIQUE constraint | T-15, A-05, ConcurrencyIT | None | Met |
| NFR-003 | Requester: privacy | Spring Security; JWT; role checks | T-14, T-16, T-24, A-04, E-03 | D-11, D-12; no independent review | Partially met |
| NFR-004 | Staff: availability | Not hosted | None | Carried to future work | Not met |
| NFR-005 | Requester: usability | Interface only | None | Carried to future work | Not met |
| NFR-006 | Management: accountability | AuditLogService; status_history; append-only trigger | T-02, T-07, A-01, RollbackIT | None | Met |
| NFR-007 | Sponsor: near-zero cost | Free tooling only | No billing evidence | Not hosted | Partially met |

Outcome: 18 requirements Met, 2 Partially met, 3 Not met. The Not met items need a hosted environment, load, or real participants. They are disclosed, not hidden.

# 50. Final Deployment and Go-Live Decision

Declared state: remaining in staging, using a simulated staging environment (Docker Compose with a separate PostgreSQL container, a jar built from the tagged commit, untracked .env file). The recommendation is a no-go for production with real users. The team must confirm it.

//GitGud Team agrees to this 18/10/2026

## 50.1 Staging evidence available

-  Dockerfile and docker-compose.yml (profile "full" starts the database and the application); .env.example; Flyway migrations V1 to V3 run on a fresh database.

-  Separate least-privilege database roles; the application role cannot change the audit tables (checked on PostgreSQL).

## 50.2 Why production is a no-go

| Blocking concern | Requirement / risk | Consequence of releasing now | What must be resolved first |
| --- | --- | --- | --- |
| Default profile is dev, which loads the demo seed (accounts sharing one demo password). No start-up guard. | D-05, R-018, NFR-003 | An unconfigured deployment exposes known accounts. | Remove the default profile, fail start-up when dev is active in a hosted setting, add a test. |
| Role passwords were committed to the repository history. | D-11, ASR-02 | Database credentials are public to anyone with repo access. | Rotate all role passwords; keep them only in .env or a secret store. |
| No login rate limiting; token cannot be revoked; no independent security review. | D-12, NFR-003, ADR-M3-01 | Credential guessing against real requesters' personal data. | Add limiter; get a lecturer or peer review; run CodeQL. |
| No CI run; 33 integration tests and ArchUnit rules never executed; P-01 not run. | R-019, NFR-001 | Database behaviour and speed under load are claimed, not shown. | Run CI to green; run P-01 and record results. |
| No build version on the health endpoint; no tested backup and restore. | D-10, TD-05 | Cannot prove which build is running or recover from data loss. | Expose version and commit; record one pg_dump restore. |
| Overdue thresholds are a 72-hour placeholder. | FR-014, TD-02 | Management would act on guessed overdue figures. | Confirm thresholds per category with the sponsor. |

## 50.3 Final release classification

CONDITIONALLY READY as a staging and demonstration build: the functional scope is complete and the main integrity, audit and access-control rules are tested. NOT READY for production use with real requesters, for the reasons above. This replaces the M3 provisional classification of NOT READY. It becomes final only after the CI run and the items marked outstanding.

## 50.4 Rollback

Redeploy the previous tagged image. Flyway only moves forward, so take a pg_dump before deploying a build with a new migration. Staging holds synthetic data only. The restore has not been rehearsed (TD-05).

# 51. Final Project Reflection and Conclusion

| Area | Conclusion from the evidence |
| --- | --- |
| Original problem and value | The final product addresses the problem in Section 1: one controlled record for a request, with ownership, an audit trail and management reporting. All 16 functional requirements are implemented. The value has been shown in a demonstration, not in use by real requesters. |
| Scope | Scope Completion is 82.6% (Section 45). No functional scope was dropped. The shortfall is all non-functional criteria that need hosting, load or participants. No scope change altered the baseline. |
| Quality | Confidence comes from tests across several levels for the three highest-priority drivers: audit, confidentiality and integrity (Section 46). Uncertain: behaviour under load, behaviour on a hosted platform, an independent security view, and the integration tests until CI runs. |
| Risks, defects and debt | Resolved: the divergent branches, missing authentication, the rejected state, the minimum description length, the PR template, TD-01 and TD-04. Remaining: committed passwords, the dev default profile, no login rate limiting, placeholder overdue thresholds, no restore test. |
| Engineering decisions | Three decisions had the clearest consequences (Section 48.3): the storage interfaces made the late merge possible; the database-first constraints gave protection the application alone would not; building the layers apart (R-004) caused the largest rework. |
| Team and project execution | The work was split across branches that did not meet until late (R-004, R-017). That, not any technical limit, most affected delivery of the original commitments and the time left for CI and load testing. |
| Future | First: close the Section 50.2 blockers and obtain a green CI run. Then host it, run P-01 and a 30-day uptime window, run a usability session, agree overdue thresholds with the sponsor, add a manager action screen, and consider refresh tokens and revocation. |

Conclusion: CivicConnect delivers what it committed to functionally and is a sound basis for a pilot, but the team is not claiming production readiness. The project was concluded, not just stopped: every M1 commitment has a final status, every important M3 issue has a recorded outcome, and the unresolved items are named with their consequence.

# 52. Known Limitations and Future Work

-  Notifications are in-app only; there is no email or SMS.

-  Managers can view reports and, through the API, act on requests; the web interface offers them no action screen (D-13).

-  Tokens cannot be revoked and there is no refresh flow or login rate limiting.

-  Overdue thresholds default to 72 hours for every category (TD-02).

-  Submission time comes from status_history; reporting speed on a large history is unmeasured (TD-03).

-  The mock API differs from the real backend for invalid transitions (400 against 409).

-  Uptime, usability and cost over time (NFR-004, NFR-005, NFR-007) are unmeasured.

-  Deferred by design: automated assignment, satisfaction survey, public dashboard, payments, dispatch integration, native apps.

# 53. Final Submission Checklist and Outstanding Actions

## 53.1 Brief checklist (Final Project brief, Section 16)

| Item | Status | Where |
| --- | --- | --- |
| One final integrated product/version is identified | Merge pull request #45 from Nicholas005/Hosting-PED-Control | Section 42 |
| Finalisation and stability prioritised over new features | Ready | Section 43.2 |
| Every significant M1 commitment has a final status | Ready | Section 44 |
| Partially / not implemented scope explained honestly | Ready | Sections 44.2, 45 |
| Deferred and out-of-scope work not treated as failed | Ready | Section 44.3 |
| Critical final user journeys demonstrable | Ready (local); repeat on the tagged build | Section 46.2 |
| Important M3 issues have a final status | Ready | Sections 35, 36, 47 |
| Existing critical verification evidence still supports the final version | Ready | Section 46 |
| No new M4 test-count target created | Ready | Section 46 |
| Existing RTM updated, not recreated | Ready | Section 49 |
| PED v3.0 finalised as PED v4.0 | Ready | Cover, Section 42 |
| Risk, Defect, Decision, Debt and AI records concluded | Ready for review; AI register student names and dates are outstanding | Sections 35 to 37, 40, 47, 48 |
| Known limitations and future work stated | Ready | Section 52 |
| Team can conclude how far M1 scope was delivered | Ready | Sections 45, 51 |
| Presentation shows the combined product, not every screen | Ready | Brief Section 12 |
| Every student prepared for the defence | All Members Ready | Brief Section 14 |

## 53.2 Outstanding actions before submission

| Action | Section | Suggested owner | Done |
| --- | --- | --- | --- |
| Merge the final work to main through reviewed PRs; run CI to green; tag the release; record tag and 40-character hash | 42 | Nicholas Armin Vronka | ☐ |
| Record the CI run URLs (green, one blocked failing run, final tag) | 30, 42 | Michiel Coenraad TerBlanche | ☐ |
| Switch on branch protection (required CI check, two approvals), secret scanning, CodeQL and Dependabot in GitHub settings | 29, 30 | Michiel Coenraad TerBlanche | ☐ |
| Link two PRs showing real review comments, responses and re-approval | 29 | Team | ☐ |
| Rotate all database role passwords (D-11) | 50.2 | Rivan Maritz | ☐ |
| Remove the dev default profile and add the start-up guard (D-05); add a test | 35 | Michiel Coenraad TerBlanche | ☐ |
| Expose build version and commit on /api/health (D-10) | 34 | Michiel Coenraad TerBlanche | ☐ |
| Decide on login rate limiting (D-12): implement or record as a blocker | 50.2 | Rivan Maritz | ☐ |
| Settle A-02: change Section 32.3 to 400 or change the API (D-08) | 32.3 | Team | ☐ |
| Run P-01 and record environment and result (or leave NFR-001 at Not met) | 33 | Rivan Maritz | ☐ |
| Record one pg_dump backup and restore (TD-05) | 34 | Rivan Maritz | ☐ |
| Confirm overdue thresholds per category with the sponsor (TD-02) | 36 | Team | ☐ |
| Approve or reject CC-01 to CC-06 and ADR-M3-01; renew the Section 24 sign-off | 24, 48 | Rivan Maritz | ☐ |
| Request a lecturer or peer security review (NFR-003) | 39 | Rivan Maritz | ☐ |
| Add a test across midnight SAST | 39 | Nicholas Armin Vronka | ☐ |
| Complete the AI register rows (student, dates) and have the team confirm every draft status | 40 | Team | ☐ |
| Re-score Section 45 after the CI run | 45 | Team | ☐ |
| Fill in the date submitted; update the Contents; export PED v4.0 to PDF | 42 | Michiel Coenraad TerBlanche | ☐ |
| Prepare the demonstration and individual defence (brief Sections 12 and 14) | - | Each member | ☐ |

# References

Gamma, E., Helm, R., Johnson, R. & Vlissides, J., 1994. Design Patterns: Elements of Reusable Object-Oriented Software. Reading, Massachusetts: Addison-Wesley Professional.

Refactoring Guru, 2014. 1. [Online] 
Available at: https://refactoring.guru/design-patterns/observer
[Accessed 14 September 2026].